No.218 - 2021: Third Session, Sixth Legislature

GAUTENG PROVINCIAL LEGISLATURE

========================

ANNOUNCEMENTS,

TABLINGS AND

COMMITTEE REPORTS

========================

Tuesday, 15 June 2021

# ANNOUNCEMENTS

none

# TABLINGS

# none

COMMITTEE REPORTS

1.	The Chairperson of the Economic Development, Environment, Agriculture and Rural Development Portfolio Committee, Hon. L J Lasindwa, tabled the Committee’s Oversight Report on the Fourth Quarterly Performance Report of the Department of Agriculture and Rural Development for the 2020/21 financial year, as follows:

COMMITTEES QUARTER OVERSIGHT REPORT ON DEPARTMENT / ENTITY PERFORMANCE

Adopted Portfolio Committee on Economic Development, Environment, Agriculture and Rural Development Oversight Report on the 4th Quarterly Report of the Gauteng Department of Agriculture and Rural Development for the 2020/2021 Financial Year

| Committee Details |  | Department / Entity Details |  |
| --- | --- | --- | --- |
| Name of Committee | Economic Development, Environment, Agriculture and Rural Development Portfolio | Name of Department / Entity | Gauteng Department of Agriculture and Rural Development |
| Which Financial Year | 20/21 | Dept. Budget Vote Nr. | 11 |
| Which Quarter | 4th | Hon. Minister / MEC | Mr Parks Tau |
| Committee Approvals |  |  |  |
|  | Name |  | Date Considered by Committee |
| Hon. Chairperson | Ms Lindi Lasindwa |  | Friday, 11th June 2021 |
| Adoption and Tabling |  |  |  |
| Date of Final Adoption by Committee |  |  | Scheduled date of House Tabling |
| Friday, 11th June 2021 |  |  |  |

NOTES:

- When expressing monetary amounts, please use South African Rand only “R” and express the full Rand amount with no cents

- When expressing percentage, please use the “%” sign and round off to two (2) decimal places

- When analysing Department / Entity performance, please do NOT copy and paste the Department / Entity performance / budget tables. These need to be analyzed.

- In the Executive Summary, include just the strategic or high level “Snap-shots” of the required information. Details will be provided later in the report under “Programme Achievement”

[Note: Please remember to “update” the table of contents just before printing or forwarding]

Contents

i.	ABBREVIATIONS	6

ii.	SUMMARY	7

iii.	INTRODUCTION	11

iv.	PROCESS FOLLOWED	12

1.	OVERSIGHT ON DEPARTMENT / ENTITY ACHIEVEMENT OF STRATEGIC PRIORITIES	13

2	OVERSIGHT ON DEPARTMENT / ENTITY ACHIEVEMENT OF APP TARGETS	14

3	OVERSIGHT ON DEPARTMENT / ENTITY PROJECT MANAGEMENT	16

4	OVERSIGHT ON DEPARTMENT / ENTITY FINANCIAL PERFORMANCE	17

5	OVERSIGHT ON DEPARTMENT / ENTITY RESOLUTIONS AND PETITIONS MANAGEMENT	19

6	OVERSIGHT ON DEPARTMENT / ENTITY PUBLIC ENGAGEMENT	21

7	OVERSIGHT ON INTERNATIONAL TREATISE / AGREEMENTS	22

8	OVERSIGHT ON DEPARTMENT / ENTITY GEYODI EMPOWERMENT	23

9	OVERSIGHT ON DEPARTMENT / ENTITY COMPLIANCE WITH FIDUCIARY REQUIREMENTS	24

10	OVERSIGHT ON A CAPACITATED PUBLIC SERVICE	25

11	OVERSIGHT ON ANY OTHER COMMITTEE FOCUS AREA	26

12	COMMITTEE FINDINGS / CONCERNS	27

13	COMMITTEE RECOMMENDATIONS	28

14	ACKNOWLEDGEMENTS	29

15	ADOPTION	29

# ABBREVIATIONS

| Abbreviation | Full Wording |
| --- | --- |
| AEL | Atmospheric Emission License |
| APP | Annual Performance Plan |
| BkB | Bontle Ke Botho |
| DALRRD | Department of Agriculture, Land Reform and Rural Development |
| DBSA | Development Bank of South Africa |
| GEYODI | Gender, Youth, Persons living with Disabilities |
| GPEMF | Gauteng Provincial Environmental Management Framework |
| GGT-2030 | Growing Gauteng Together – Our Vision 2030 |
| GPL | Gauteng Provincial Legislature |
| GWIS | Gauteng Waste Information System |
| SOM | Sector Oversight Model |
| MTSF | Medium Term Strategic Framework (in this case, relating to 2019-2024 Term of Office) |
| NDP | National Development Plan |
| PGDP | Provincial Growth and Development Plan |
| POE | Portfolios of Evidence |
| PPP | Preferential Procurement Plan |
| PRAAD | Policy Reasonable Accommodation and Assistive Devices |
| PwDs | Persons living with Disabilities |
| RISDP | Regional Indicative Strategic Development Plan |
| SDGs | Sustainable Development Goals |
| TER | Township Economy Revitalisation |
| TID | Technical Indicator Description |

# SUMMARY

ii. [Summary of the report]

[Note: Only snapshots or “One-Liners” or Bullet Points of the most important / strategic achievements. No details please]

Strategic Priorities High level summary of Committee’s overall assessment of the Department / Entity achievement of relevant strategic priorities for the period under Review

The Committee noted that the Department's focus is on harnessing and maximising the economic potential of the province's agricultural sector and ensuring food security for all. Moreover, Agriculture has been identified as one of the province's eleven key economic sectors. Nationally, the sector is set to create one million jobs by 2030. The Department committed to ensure that the sector is involved with all interventions to radically transform, modernise and reindustrialise Gauteng. Apart from the alignment of its programmes and policies to the GPG TMR, the department also ensures alignment to the National development Plan (NDP). The Department planned for and reported on a total of 77 indicators as at the end of the fourth quarter. Overall, the Department achieved 74% (57) of its fourth quarter targets. 26% (20) of targets were not achieved. This can be attributed to non-achievement of 5 indicators in Programme 1( Administration), 7 in Programme 2 (Agriculture and Rural Development) and 8 in Programme 3 ( Environment)). The Department regressed in its attainment of Annual Performance Plan targets in the current quarter and achieved 74% when in the third quarter, they had attained 84%.

Department / Entity APP Achievement An overall Summary of whether the Committee thinks the Department / Entity Non-Financial Performance is sound and prudent

The Committee noted that the Department spent R282 061 000 of the quarter appropriation (R322 279 000) which is the equivalent of 87,52% of budget for the quarter. The Administration programme spent R56 826 000 of R56 574 000 which is 100,45% of quarter budget. The Agriculture and Rural Development programme spent R47 037 000 of R93 002 000 (66,41%) and the Environmental Affairs programme spent R132 233 000 of R125 666 000 (105,23%). The year-to-date effect of budget utilization for all 3 programmes meant that both the Administration and Environmental Affairs Programmes are at levels commensurate with this time in the budget cycle at 100,10% and 102,06% respectively of expenditure whereas the Agriculture and Rural Development Programme returned concerning expenditure levels of 88,92% of year-to-date usage. The under expenditure translates to just over R40 million that remains unused and will have to be returned to the Provincial Treasury. The Committee further noted that the Department requested roll over of R23 million for use of these funds in the 2021/22 Financial Year.

An analysis on whether (and if so, the extent to which) the Department / Entity Programmes / Projects are indeed achieving its Strategic Objectives / Service Delivery Outcomes for the period under review.

The Committee notes with concern that the Department has consistently been under performing even before the Covid 19 pandemic. The Committee continues to encourage the Department to ensure that the service delivery mandate is achieved.

Department / Entity Project Management Overall Summary on management and delivery of Department / Entity Projects

The Committee continues to note with concern on the various capital funded projects that the Department is managing in the current financial year and over the Medium-Term Economic Framework (MTEF) period which have run for a long period without completion.

Financial Performance An overall Summary of whether the Committee thinks the Department / Entity Financial Performance is sound and prudent

The Committee notes with concern that the financial performance of the Department during the quarter under review paints a rather concerning picture with expenditure for one of the programmes at the forefront of service delivery – Agriculture and Rural Development - below the levels required at this time in the budget cycle. This as agriculture was deemed an essential service by the National government in the 2020/21 financial year because of the important role it plays in the country in helping to address food security. As a result, some funds have not been utilized and have had to be returned to Treasury and it is hoped that the roll over request made will be granted so that these funds are again pumped into the Department’s reserves for use in the 2022/23 financial year. The Administration Programme was allocated R56,57 million and the expenditure for the quarter is R56,82 which translates to 100,45% expenditure and had the quarter budget depleted by R252 thousand. The Environmental Affairs Programme was allocated R125,66 million and utilized R132, 23 million which translates to 105% expenditure for the quarter and the budget was exceeded by R6,56 million. The Agriculture and Rural Development Programme was allocated R140,03 million and utilized R93,00 million which translates to 66,41%. This means that the programme has an amount of money to the tune R47 million that remains unutilized and has to be surrendered to Treasury.

Resolutions Management An overall Summary of the Committee’s assessment of Department / Entity Resolutions Management

Resolutions not yet due and analysed for the period under review.

Petitions Management An overall Summary of the Committee’s assessment of Department / Entity Petitions Management

9

Public Engagements An overall Summary of the Committee’s assessment of Department / Entity Public Engagements

None

International Agreements Overall Summary on Department / Entity implementation of relevant Internal Agreements / Treaties [Only if applicable] [Applicable only to OCPOL / OoP]

[Enter information here]

GEYODI Empowerment Overall Summary on Department / Entity achievement on actual GEYODI empowerment in communities

The Committee noted with concern as the Department did not manage to achieve its procurement target for youth and Pwd groups. The Department’s biggest expenditure is currently on contracts that were already secured through an open tender process. . The Department will put measures in place to pursue a more targeted and deliberate approach towards businesses owned by designated groups, through inclusion of Preferential Procurement Plan (PPP) regulation 4, prequalification criteria as a condition in tender request to subcontract 30% of the tender to designated groups. The Department reported that it is challenging to implement preferential procurement to designated groups because proper market research or feasibility studies are not conducted to check if it is feasible to subcontract and if the township-based businesses have capacity to provide goods and services required in order for the department to use Regulations 4 and 9 when sending out the tender request. The Committee acknowledges that the Department appointed a task team to deal with the issue of preferential procurement in order to support and advance the designated groups and also to be able to meet the Department targets.

Fiduciary Compliance Overall Summary on Department / Entity Compliance with fiduciary requirements

The format of the Gauteng Department of Agriculture and Rural Development’s 4th Quarterly report of 2020/21 financial year is in compliance with standard requirements (targets per quarter, expenditure per programme, expenditure per economic classification). However, it should be noted that the new structure of the report makes no provision for revenue generated, economic classification, makes provision for an update on the status of capital projects the Department is involved in.

Capacitated Department / Entity An overall Summary of whether the Committee thinks the Department / Entity is adequately capacitated and resourced to carry out its functions and discharge its mandates

The Committee has always been of the view that all Departmental critical vacant positions should be filled in order to ensure that service delivery imperatives are attained.

Any other Committee Focus Area (if relevant / applicable and Requirement) High level summary of any other area of Department / Entity performance with respect to its Quarter Report that the Committee wishes to report on, which is not already included in any of the above Focus Areas.

[Enter information here]

Summary of Committee Findings High level summary of Committee findings. Broadly, which aspects do they relate to

The Committee continuously observes that the Department fails to spend its annual budget and never meets its planned targets. Moreover, there is ’; - Lack of improvement on spending the allocated budget, continuous underperforming, and not achieving planned targets. - The negative impact that COVID-19 has had on farmers in the Province. - Failure to support the Township Economy Revitalization (TER) strategy and implementation thereof. - Continuous failure to align its budget with its planned targets, as under expenditure is observed in Agriculture and Rural Development and Environmental Affairs Programme. - Lack of completing infrastructure projects and spending in goods and services due to tender processes that are being implemented through the open tender system

Summary of Committee Recommendations High level summary of Committee Recommendations. Broadly, which aspects do they relate to

The Committee recommends that the Department provide; - A quarterly update on how all underachieved targets under the Agricultural sector will be achieved as lockdown regulations are eased. - Operational plans in place to ensure that the Agricultural Sector in the Province is supported. - Comprehensive report on the implementation of the Township Economy Revitalization to support the planned target of 40 percent on township spending. - Provide detailed quarterly reports on how it will align all its Departmental targets with its expenditure, and how the service delivery mandate will be achieved. - To further report on corrective actions that will be undertaken by the Department on the under expenditure experienced by the Agriculture and Rural Development.

# INTRODUCTION

The Economic Development, Environment, Agriculture and Rural Development Portfolio Committee exercises oversight and scrutiny over the Gauteng Department of Agriculture and Rural Development herein referred to as the Department. This includes planning, budgeting, financial management and reporting by the Provincial Department of Agriculture and Rural Development. In line with the provisions of the Constitution of the Republic of South Africa (1996), the Public Finance Management Act (PFMA) (1999) creates the basis on which oversight by Legislatures should be exercised. It clearly outlines areas of service delivery that should be reported on, including the responsibilities of officials and the role of the Legislature in cases where reports have to be tabled. This report primarily focuses on examining whether the budget allocated for the Department is aligned to key government strategic priorities. Furthermore, the report assesses whether the objectives of the Department correlate with the intended outputs as well as outcomes. The Portfolio Committee intends to interrogate and assess the overall departmental performance through in year monitoring and make findings on the performance of Departmental programmes during the 4th Quarter for the 2020/21 FY. The Gauteng Provincial Legislature’s oversight methodology stipulates that when analysing the budget, the variables of the Sector Oversight Model (SOM) must be considered. Given that SOM variables are interrelated, priorities, inputs (capital and current), outputs and outcomes should be considered one against the other.

# PROCESS FOLLOWED

- The Speaker formally referred the 4th Quarterly Performance Report of the Gauteng Department of Agriculture and Rural Development for the 2020/21 financial year to the Economic Development, Environment, Agriculture and Rural Development Portfolio Committee for consideration and reporting.

- At the meeting held on Friday, 14th May 2021 the Committee Researcher tabled an analysis of the performance report of the 4th quarter. On Tuesday, 25th May 2021 the Gauteng Department of Agriculture and Rural Development presented the 4th Quarterly Performance Report for the 2020/21 financial year to the Portfolio Committee focusing on the departmental financial and non-financial performance.

- On Friday, 11th June 2021, the Portfolio Committee deliberated and adopted the draft oversight report on the 4th Quarter performance of the Department. The report was submitted to the Proceedings Unit for tabling and consideration by the House.

# OVERSIGHT ON DEPARTMENT / ENTITY ACHIEVEMENT OF STRATEGIC PRIORITIES

1.1 THE DETAILS ON Department / Entity achievement on relevant Strategic Priorities for the period under review]

The Committee noted that the Department's focus is on harnessing and maximising the economic potential of the province's agricultural sector and ensuring food security for all. Moreover, Agriculture has been identified as one of the province's eleven key economic sectors. Nationally, the sector is set to create one million jobs by 2030. The Department committed to ensure that the sector is involved with all interventions to radically transform, modernise and reindustrialise Gauteng. Apart from the alignment of its programmes and policies to the GPG TMR, the department also ensures alignment to the National development Plan (NDP). In ensuring that, the Department reported that; - 11 stakeholders contributed to the implementation of Rural Development programme through quarter 4 progress reports. - 149 households were supported with agricultural food production initiatives and a further 13 school food gardens and seven community food gardens - No Stakeholders were supported with COVID 19 Awareness Training. - One (1) Gauteng Rural Social Compact Plan signatory was supported. - 58 queries were resolved via email on GPG Common Platform that were requesting funding, farming information, land, and municipality support complaint. - 100 percent of waste licence applications were finalized within legislated timeframes. - 2 222 permits were issued within legislated timeframes - 91 percent of completed EIA applications were finalised within legislated timeframes - 5 102 export control certificates issued - 1 811 epidemiological units were visited, and 11 243) laboratory tests performed - 64 smallholder producers and 29 women producers were supported - 23 smallholder producers were supported in Sedibeng and West Rand

# 2	OVERSIGHT ON DEPARTMENT / ENTITY ACHIEVEMENT OF APP TARGETS

2 [THE DETAILS ON DEPARTMENT / ENTITY APP PERFORMANCE]

Number of APP targets relevant for this Quarter

77

Number of APP targets for this Quarter that have been achieved during this Quarter

57

Percentage of APP targets for this Quarter that have been achieved during this Quarter

74%

Percentage of APP achievement for the previous Quarter (for Comparison)

84%

Main areas in the APP that have experienced non-achievement or over achievement during this Quarter

The Administration Programme had the lowest number of unachieved targets at 5, the Agriculture and Rural Development 7, whilst the Environmental Affairs Programme recorded the highest level of unachieved targets at 8.

Main reasons provided by the Department / Entity for non-achievement or over achievement of its APP during this Quarter

The Department managed to spend 88% of its projected budget for the 4th quarter that is R282 Million of the projected R322 million. The 44% under expenditure that occurred in Programme 2 can be attributed to late finalisation of purchase orders and the Service provider could not deliver timeously, or deliveries were made before financial year end closure. As such, payment could not be processed before last payment run. All infrastructure projects implemented by DBSA were not completed as at the end of the financial year, and only management fees were claimed form the Department. The five (5%) overspending in Programme 3 can be attribute to the clean-up and decontamination programme to prevent the spread of Covid-19 pandemic and additional resource allocated to the Emfuleni waste management programme.

Measures in place (with timeframes) to correct the deviation in targets for this Quarter and to prevent recurrence of such or similar deviation

The Department reported that the following mitigating measures will be implemented to remedy the under expenditure. - Treasury is aware of all system related problems, but it is out of the Department's control, the invoice rejecting to exception will still be a problem, because it will be cleared on the following payment run, still exceeding the 15 days. These invoices were however processed within 30 working days. - The Department will therefore continue to implement measures put in place to pursue a more targeted approach towards businesses owned by Youth and PwDs. The Departmenthas established a task team to deal with the issue of preferential procurement in order to support and advance the designated groups and meet these targets - Management will inform DID of the office needs as per Service Level Agreement (SLA) so that the Department of Infrustructure Development (DID) can procure office accommodation for the Department. The Department will also request permission from DID to manage own lease accommodation procurement if the measures stated above fail and also request Treasury’s permission for deviation where procurement threshold requires Treasury decision. - The Department will identify the tenders during procurement planning to be subcontracted to township-based service providers by applying regulation 4 and 9 of PPR 2017. - Engage Department of Agriculture, Land Reform and Rural Development (DALRRD) to ensure that business plans approvals are fast-tracked in next financial year 2021-2022. - Farmers would be informed about the importance of strengthening their biosecurity at farm levels to increase visits to the farms. - The annual target has been achieved and the department will continue to participate in RT contracts at National Treasury. - Partnerships with other organizations will be explored to leverage more resources for food gardens. - The projects have been approved and will be implemented by DBSA. The Committee acknowledged the mechanism putin place to ensure targets are achieved in the next quarter.

A summarized analysis on the Department / Entity performance per Programme for the period under review

The Gauteng Department of Agriculture and Rural Development funds three programmes namely; Administration, Agriculture and Rural Development as well as Environmental Affairs. The Department planned for and reported on a total of 77 indicators as at the end of the fourth quarter. Overall, the Department achieved 74% (57) of its fourth quarter targets. 26% (20) of targets were not achieved for the fourth quarter. This can be attributed to non-achievement in Programme 1: Administration (5), Programme 2: Agriculture and Rural Development (7) and Programme 3: Environment (8). PROGRAMME 1: ADMINISTRATION The programme’s purpose is to conduct the overall management and provides an administrative support function The Department reported that 94% of invoices were paid within 15 days for the quarter under review. The main reasons provided for exceeding the 15 day are attributed to some payments not clearing for the final payment run due to system closure for the December 2020 festive period; two invoices which were submitted caused duplication on SAP system and an invoice did not interface on to BAS. The system’s challenges have been escalated to Gauteng Provincial Treasury to assist in resolving them. These led to delays in payment run which will exceed 15 working days. However, the Department is commended for processing all invoices for payment to suppliers within 30 working days. The Committee continues to be concerned with the target for businesses owned by Youth and People with Disabilities (PwDs) which was not met. The Department acknowledges the weakness in supporting the targeted businesses owned by this targeted group in the province. To realise the achievement of set targets, the Department is working in collaboration with the DSD and DED to intensifyd Supplier Development intervention to equip them to transact with the Department when the requests for quotations (RFQ’s) for procurement below R500 000 are made. The Department will therefore continue to implement measures put in place that is to pursue a more targeted approach towards businesses owned by Youth and PwDs. GDARD has established a task team to deal with the issue of preferential procurement to support and advance the designated groups and meet these targets. The target for businesses owned by Women was overachieved by 3% against the target of 20% for the quarter. The Committee noted with concern that the Department did not achieve the target on township spend and acknowledges the weakness in supporting the targeted businesses owned by thise target group in the province. It is reported that measures will be put in place to pursue a more targeted and deliberate approach towards businesses owned by designated groups, through inclusion of PPP regulation 4, prequalification criteria as a condition in tender request to subcontract 30% of the tender to designated groups. It is also working with DED to intensify Supplier Development workshops. The Department is commended for striving to reduce and maintaining the vacancy rate below the national 10% standard and has recorded 8.4% vacancy rate at end of financial year. Similarly, senior management (SMS) female representation was increased to 56 percent against planed target of 50 percent. The continuous targeted recruitment drive and the commitment to prioritise women has yielded positive results. People with disability representation in the department surpassed the 2% national target and was sitting at 2.68%. The achievement of PwDs target could be attributed to continuous internal disclosure process during the Policy Reasonable Accommodation and Assistive Devices (PRAAD) policy workshops and targeted recruitment drives. The Policy Reasonable Accommodation and Assistive Devices (PRAAD) Policy workshops were conducted with the intension to encourage employees to disclose their disability status. All these achievements could be attributed to the department’s direct and deliberate interventions like targeted recruitment and ring fencing of certain positions for these targeted groups. With regards to number of work opportunities created through Tshepo 1 Million, a total of 1 305 work opportunities have been created in quarter 4. There was an upscale in Expanded Public Works Progarmme (EPWP) job opportunities in March 2021. Ntirhisano is a Community Outreach programme initiated by the Provincial Government to address service delivery issues. It is led by the Premier and all Members of the Executive Council in their specific areas. Community members raise their challenges and its resolutions are prioritised through this programme. GDARD continues to participate in the Ntirhisano programme and is mostly responding to challenges related to farmer support, land availability and waste management. The Department received 58 queries and/or complaints via emails, walk-ins and GPG Common Platform (Dynamics) and were all resolved. The queries and/or complaints were about funding support, infrastructure support, land reform, tribal issues, Solidarity Fund voucher and greening. PROGRAMME 2: AGRICULTURE AND RURAL DEVELOPMENT The purpose of this programme is to consolidate and enhance the role of the agricultural sector in radically transforming, modernising and re-industrialising Gauteng. The programme is also intended to support viable and sustainable agricultural enterprises, increase access to food security for all, and ensure comprehensive rural development. Sustainable Resource Management The Sustainable Resource Management (SRM) is responsible to manage and coordinate the provision of sustainable resource management services. The Department did not achieve its planned targets for number of hectares of agricultural land rehabilitated, as delays in the approval of the Land Care Conditional Grants Business Plan by DALLRD, led to the non-achievement of the planned target. The Department will engage DALLRD to ensure that business plans approvals are fast-tracked in next financial year 2021-2022. Through community-based projects (Conservation Agriculture) and Youth supporting permaculture gardens, 66 green jobs were created in seven (7) schools (Barcelona Primary school, Ecaleni Primary School, Tiisetso Bekezela Primary School, Thorn Tree Primary School, Kamogelo Primary School, Olifantsvlei Primary School, and Ondertespoort Primary School). Farmer Support and Development The Farmer Support and Development (FSD) Directorate is responsible to expand access to agri-food value chain opportunities, promote agricultural development within the land and agrarian reform initiatives in the province and maximise food security, through provision of sustainable agricultural development support to subsistence, smallholder and commercial farmers, provision of agricultural infrastructure support coordination, rendering of extension and advisory services , training and capacity building to farmers. The delay in planting of crops by farmers resulted in 624 hectares planted for food production in this quarter not being achieved. Although the target was not achieved for the quarter under review, the annual target has been achieved. The Committee noted that due to disease outbreaks, there has been a limited movement in poultry and piggery farms. Biosecurity at farm levels was not compromised due to drastic reduction in farm visits. However, this has adversely affected number of smallholder producers supported with agricultural advice. A total of 307 smallholder producers were supported with agricultural advice against a target of 400 for the quarter under review. Furthermore, 149 households were supported with agricultural food production initiatives, and 13 school food gardens were also supported with food production inputs, in this quarter. Research and Technology Development Services The Research and Technology Development Services (RTDS) Directorate is responsible to render expert and needs based research, development and technology transfer services impacting on development objectives. The Project Initiation Report (PIR) was not approved by the Gauteng Provincial Treasury which resulted in no Agri-parks being established. However, the projects have been approved to be implemented by DBSA. Seven (7) Agri-parks were in operation at the end of the fourth quarter. One Agri-Park in Merafong Agripark was not operating due to vandalism of fence, electrical cables and lack of water during the year. However, seven women benefitted from those Agri- parks and 1 Agrotropolis initiative supported in this quarter. Agro-processing and Agricultural Economics Services The Agro-processing and Agricultural Economics Services (AES) Directorate is responsible to manage and coordinate the provision of agriculture, agro-processing and technical services. The Department managed to support 127 agri-businesses with production economic services to make informed decisions on their farms and produce. The partnership with the Perishable Product Export Control Board (PPECB) resulted in 15 agri-businesses supported to access markets and sell their agricultural produce. Furthermore, the Department managed to support nine (9) agro-processing initiatives through ensuring food safety and providing agro-processing equipment. Agricultural economic information responses were provided to farmers by offering various agricultural economic and technical advisory services. PROGRAMME 3: ENVIRONMENTAL AFFAIRS The programme is responsible for promoting the equitable use of the ecosystem; goods and services; and contributing to economic development by managing biodiversity and its components, processes, habitats and functions. The programme consists of four sub-programmes namely; Environmental Policy, Planning and Coordination; Environmental Quality Management, Compliance and Enforcement as well as Biodiversity Management. Compliance and Enforcement The objective of this unit is to manage the development, and implementation of environmental compliance monitoring systems, enforcement of legislation and environmental authorisations. The Department handed three (3) criminal investigations over to the National Prosecuting Authority (NPA) for prosecution against a target of five (5). This was due to outstanding witness statements in three matters under investigation and as such these matters could not be finalised for handing over to the NPA. Additionally, seven (7) S24G applications were finalised against the planned quarterly target of six (6). These include an environmental authorisation for unlawful development of an agropolitan city in Bronkhorstspruit; an environmental authorisation for unlawful processing of animal waste into biodiesel and food in Cullinan; and an environmental authorisation for the unlawful development of a tourism facility within the Dinokeng Game Reserve. The Department managed to designate 15 environmental inspectors against a planned target of four (4). This was due to requests from various municipalities and officials that had to be re-designated as Environmental Management Inspectors (EMI). The Committee encourages the Department to make follow-ups on the outstanding investigations to ensure that the annual target is met. Impact Management The purpose of this unit is to manage the implementation of environmental impact mitigation to promote sustainable development and a safe healthy environment. The Committee noted that not all Environmental Impact Assessment applications that were received were finalised within the legislated timeframe as the Department managed to finalise 91% against a planned target of 100%. The EIA Online System email notification for uploaded reports was not working for two weeks during February 2021 and March 2021 and therefore caused delays. The matter was reported to the service provider and subsequently resolved. Biodiversity Management The purpose of this unit is to promote equitable and sustainable use of ecosystem goods and services to contribute to economic development. The Department planned on issuing 2 000 permits within legislated timeframes but managed to issue more by 222. This was due to fewer applications being received from the public than anticipated. It is reported that some of the permits included a permit to capture birds for ringing and immediate release; a permit to export or remove from the Province dead game or game products; and a permit to act as a hunting outfitter. One (1) biodiversity economy initiative was planned but could not be achieved due to two bids received not meeting the threshold for evaluation in terms of functionality. Furthermore, the Department planned to expand the number of hectares in the conservation estate to 87 412 but this could not be achieved as the hectares remained at 87 012. This was due to Covid pandemic delaying many of the due diligence biodiversity stewardship processes that needed to be conducted including procurement processes i.e publishing of the notice in the government gazette. Environmental Empowerment Services The purpose of this unit is to empower communities to manage natural resources through job creation, skills development, and awareness opportunities. The Department had planned two thousand three hundred (2 300) work opportunities through environmental programmes but could only achieve one thousand four hundred and seventy-five (1 475). This was because of COVID 19 outbreak which resulted into some projects being affected by budget cuts, delays in SCM processes and non-implementation due to ministerial directives. On the other hand, the Department exceeded the target on Extended Public Work Programmes (EPWP) ull time equivalent job jobs created. It is further noted that the Department had planned for two hundred and fifty (250) EPWP FTE jobs and managed to achieve two hundred and eighty-four (284). This was due to the implementation of long-term projects such as Environmental Awareness Graduates Programme, Bontle ke Botho (BKB) Waste Removal, BKB Greening, Indigenous Ornamental and Food Crop Nurseries Projects because of approved three (3) years tenders. The Department also managed to develop two (2) environmental education resources materials as planned.

Summarized information on any unplanned / emerging priorities reported on by the Department / Entity during the period under review

There were none unplanned or emerging priorities reported for the quarter.

Summarized information on how the Department / Entity maintains portfolios of evidence to verify its reported performance information

The verification process is intended to ensure that the reports, listings, and Portfolios of Evidence (POEs) submitted by the branches are accurate. This is done by cross checking the reports against the supporting listings and POEs. The focus areas that the Monitoring and Evaluation Unit (M&E) validates during verification include the following: - POE against TID (as it appears in an approved APP): This verifies whether the submitted POE is the one stipulated in the Technical Indicator Description (TID) or not. - Listing against POE: This verifies whether all the POEs are reflected in the listing. - Dates: This verifies whether the dates contained in the POE fall within the quarter under review. - Signatures: This verifies whether all the required signatures in the documents are appended or not. - ID copies: This is to verify the ID numbers of beneficiaries and to support the signature appended on the delivery notes. In the end, evidence and listings provided must reflect and correspond with the reported figures. If the numbers do not correspond, this is communicated to the branches for correction, resubmission, or confirmation of the figures as recounted by M&E. When all of this has been completed, the validated report, listings and POEs get stored on Planning, Monitoring and Evaluation’s electronic shared folder which is located on the Department’s internal drive. The internal shared drive which is only accessible to M&E and IT officials who have been granted access.

# 3	OVERSIGHT ON DEPARTMENT / ENTITY PROJECT MANAGEMENT

- THE DETAILS ON [DEPARTMENT / ENTITY PROJECT MANAGEMENT]

The Committee has continuously observed the lack of project management from the Department in the previous years. The Department has lacked in completing infrastructure/capital funded projects and spending in goods and services due to tender processes that are being implemented through the open tender system. The Committee conducted oversight on some of the outstanding projects and will continue to monitor as some of them date back to the previous Political Term. (the same reporting last time).

| Name of Project | Brief description of project | Start Date | End Date | Current Status | Challenges |
| --- | --- | --- | --- | --- | --- |
| Abe Bailey Nature Reserve: Construction of fence | Construction of fence | 5 Feb 2018 | 2 Jun 2022 | Feasibility | Project to be implemented by DBSA, however the IPIP was recently completed and sites visits has commenced. COVID-19 caused serious delays. |
| Diepkloof Farm in Suikerbosrand Nature Reserve: Supply and installation of fence | Supply and installation of fence | 15 Oct 2019 | 30 Nov 2021 | Project Initiation | Project to be implemented by DBSA, however the IPIP was recently completed and sites visits has commenced. COVID-19 caused serious delays. |
| Rand West Agri park: Upgrading of Agri park | Upgrading of Agri park | 30 Nov 2018 | 1 Nov 2021 | Feasibility | Project to be implemented by DBSA, however the IPIP was recently completed and sites visits has commenced. COVID-19 caused serious delays. |
| Roodeplaat Nature Reserve: Construction of new staff housing, Upgrading of Zeekoeigat Hall and sleeping quarters. | Construction of new staff housing, Upgrading of Zeekoeigat Hall and sleeping quarters. | 18 Jul 2018 | 5 Feb 2024 | Project Initiation | Project to be implemented by DBSA, however the IPIP was recently completed and sites visits has commenced. COVID-19 caused serious delays. |
| Suikerbosrand Nature Reserve: Upgrading of bulk infrastructure | Upgrading of bulk infrastructure | 1 Mar 2018 | 9 Dec 2024 | Project Initiation | Project to be implemented by DBSA, however the IPIP was recently completed and sites visits has commenced. COVID-19 caused serious delays. |
| Suikerbosrand Nature Reserve: Upgrading of Northern Water Line | Upgrading of Northern Water Line | 1 Jul 2005 | 2 May 2022 | Feasibility | DID is not ensuring that PSP provide cash flow projections and schedule indicating timelines to submit all necessary documentation. DID should indicate when the project will progress to implementation phase. |
| Tarlton Agri park: Upgrading of the Agri park | Upgrading of the Agri park | 21 Feb 2018 | 1 Mar 2023 | Project Initiation | Project to be implemented by DBSA, however the IPIP was recently completed and sites visits has commenced. COVID-19 caused serious delays. |
| Vereeniging Fresh Produce Market: Upgrading of the market | Upgrading of the market | 29 Nov 2017 | 28 Nov 2024 | Project Initiation | Project to be implemented by DBSA, however the IPIP was recently completed and sites visits has commenced. COVID-19 caused serious delays. |
| Installation of boreholes and irrigation systems. | Installation of boreholes and irrigation systems. | 31-Aug-19 | 08-Mar-22 | Project Initiation | None. |
| Various Farms – Construction of 63 boreholes. | Various Farms – Construction of 63 boreholes. | 07-Nov-17 | 11-May-22 | Construction | Delay in creating of Purchase Order. Contractor drilled where he was not permitted to drill in Ekurhuleni. Geohydrologist to confirm if any dolomite issues were encountered and borehole fit for use. |
| Various Farms – Construction of 8 Piggery structures. | Various Farms – Construction of 8 Piggery structures. | 07-Nov-17 | 31-Mar-22 | Projection Initiation | Project to be implemented by DBSA, however the IPIP was recently completed. IA to submit the sites visits schedule. COVID-19 caused serious delays |
| Procurement and Installation of rain harvesting systems at 60 schools | Procurement and Installation of rain harvesting systems at 60 schools | 21-May-18 | 01-Apr-21 | Practical Completion (100%) | Construction in progress currently at 100%. |
| Procurement and Installation of shade nets x24 locations | Procurement and Installation of shade nets x24 locations | 16-May-18 | 06-Dec-21 | Project Initiation | Project to be implemented by DBSA, however the IPIP was recently completed and sites visits completed. COVID-19 lockdown caused serious delays |
| Construction and commissioning of the 24 broiler house (2500 broilers each) and 6 Layer house (5000 layers each) | Construction and commissioning of the 24 broiler house (2500 broilers each) and 6 Layer house (5000 layers each) | 13-Mar-17 | 23-Nov-21 | Construction 76% -99% | Overall construction progress is 82% complete for the sites handed over to the contractor to date. Progress delayed by the COVID -19 lockdown. Implementing Agent is ARC for the projects. Slow progress on sites |
| Construction of 8 Biogas Plants. | Construction of 8 Biogas Plants. | 31-Jul-19 | 30-Jan-24 | Project Initiation | Client forwarded site locations and contacts for additional beneficiaries. Awaiting site visit confirmation from Internal client. COVID-19 lockdown caused serious delays |
| Farm Fences installation in 6 sites | Farm Fences installation in 6 sites | 31-Jul-19 | 22-Aug-21 | Project Initiation | Project to be implemented by DBSA, however the IPIP was recently completed. Site visits completed by DBSA. |
| Installation of boreholes and irrigation systems. | Installation of boreholes and irrigation systems. | 31-Aug-19 | 08-Mar-22 | Project Initiation | Draft PIR is requires additional information as new boreholes must be added |
| Construction of new poultry structure (5 000 capacity) | Construction of new poultry structure (5 000 capacity) | 19-Jul-19 | 14-May-21 | Project Initiation | Project to be implemented by DBSA, however the IPIP was recently completed. Site visits completed by DBSA. |
| Construction of new poultry structure (40 000 capacity) | Construction of new poultry structure (40 000 capacity) | 08-Jul-19 | 14-Nov-22 | Project Initiation | PIR to be submitted to GPT by end of November 2020. SUE provided letters for a basic EIA to be done. |
| Installation of solar water pumping system for borehole | Installation of solar water pumping system for borehole | 01-Jul-19 | 01-Jul-21 | Project Initiation | Project to be implemented by DBSA, however the IPIP was recently completed. Site visits completed by DBSA. |

# 4	OVERSIGHT ON DEPARTMENT / ENTITY FINANCIAL PERFORMANCE

4 THE DETAILS ON DEPARTMENT / ENTITY FINANCIAL PERFORMANCE

Actual amount (in Rands) allocated to the Department / Entity as budget for this entire Financial Year

R994 713 000

Actual amount projected by the Department / Entity to be spent only during the Q under review

R322 279 000

Actual amount (in Rands) spent by the Department / Entity only during the Q under review

R282 061 000

Total actual amount (in Rands) spent by the Department / Entity (Year to Date), i.e. from the beginning of this FY to the end of this Q under review

R954 495 000

Percentage (% of total budget allocation) of budget expenditure for this Q under Review only

87,52%

Percentage (% of total budget allocation) of budget expenditure (Year to Date), i.e. from the beginning of this FY to the end of this Q under review

95,96%

An analysis of how the % budget expenditure compares with the % APP achievement

Budget expenditure is at 87,52% and APP achievement is at 74%

If there was over / under spending of greater than 3% of projection, what were the main challenges that led to the over / under spending

The Department managed to spend 88% of its projected budget for the 4th quarter that is R282 Million of the projected R322 million. The 44% under expenditure occurred in Programme 2 can be attributed to late finalisation of purchase orders and the Service provider could not deliver timeously, or deliveries were made before financial year end closure. As such payment could not be processed before last payment run. All infrastructure project implemented by DBSA were not completed as at the end of the financial year, and only management fees were claimed form the Department. The five (5%) overspending in Programme 3 can be attributed to the clean-up and decontamination programme to prevent the spread of Covid-19 pandemic and additional resource allocated to the Emfuleni waste management programme. The Department’s total adjusted allocated budget was R994.7 million and it managed to spend R954.4 million that is equivalent to 96% of its total adjusted budget allocation for the 2020-2021 FY. The R40 million under-spending is due to reasons indicated above. The Department has requested roll over from Provincial Treasury to an amount of R23 million.

Mitigating measures by the Department / Entity to remedy over / under expenditure

During the second quarter, the Department has revised the Annual Performance Plan and Procurement Plans with a view to accelerate spending during quarter 3 and 4. This included reviewing the budget during the adjustment process, - Organisational structures not updated and inadequate procurement officials which weakens the capacity and capability of procurement to support the Department Mandate. - Poor implementation of Annual Procurement plan and ineffective and inefficient implementation of SCM process which affects service delivery, causing underspending by cancellation of some tenders and delays in tender processes. - -The Department is busy with re-alignment or re-structuring SCM directorate and review of structure to include all SCM functions which will respond to the increased demand of Department priorities. These structure changes were included in the Department revised Organisational structure for approval.

The Department / Entity’s achievement with respect to GEYODI responsive budgeting / procurement for the period under review

The Department did not achieve its procurement target for youth and Pwds groups. - It is reported that businesses owned by designated groups did not respond or qualifyd for these based on the quotations provided by them or these designated groups do not provide or supply these services. The Department’s biggest expenditure is currently on contracts that are already secure through an open tender process and RT contracts. The Department will put measures in place to pursue a more targeted and deliberate approach towards businesses owned by designated groups, through inclusion of PPP regulation 4, prequalification criteria as a condition in tender request to subcontract 30% of the tender to designated groups. The department thrives to achieve the target and the Department will identify the tenders and apply regulation PPP 2017 to subcontract 30% to township-based service providers during Procurement Planning. It is very challenging to implement preferential procurement to designated groups because proper market research or feasibility studies are not conducted to check if it is feasible to subcontract and if the township-based businesses have capacity to provide goods and services required in order for the department to use Regulation 4 and 9 when sending out the tender request. - The Department appointed a task team to deal with the issue of preferential procurement in the Department in order to support and advance the designated groups and to be able to meet the Department targets.

The Department / Entity’s achievement with respect to township economy / SMME / local procurement for the period under review

The Department in the fourth Quarter of the 2020-2021 Financial year did not achieve its procurement target for Township spend of 40% but managed to increase its percentage from 31% in the previous quarter to 33% in the quarter under review. The Department’s biggest expenditure is currently on contracts that are already secure through an open tender process and RT contracts. The Department will put measures in place to pursue a more targeted and deliberate approach towards businesses owned by designated groups, through inclusion of PPP regulation 4, prequalification criteria as a condition in tender request to subcontract 30% of the tender to designated groups. The department thrives to achieve the target and the Department will identify the tenders and apply regulation PPP 2017 to subcontract 30% to township-based service providers during compilation of Procurement planning.

A summary for the period under review with respect to payment of service providers within 15-30 days

The Department managed to pay 94% of invoices within the 15 days for the fourth quarter of 2020-2021. The main reasons for exceeding the 15 days can be attributed to the following: some payments did not clear for the final payment run due to system closure for the December 2020 festive period; two invoices which were submitted caused duplication on SAP system and an invoice did not interface on to BAS. The system’s challenges have been escalated to Gauteng Provincial Treasury to assist in resolving them. These led to delays in payment run which will exceed 15 working days. However, the Department managed to process all invoices for payment to suppliers within 30 working days.

A summary for the period under review with respect to fruitless, wasteful and irregular expenditure

# Fruitless and wasteful expenditure - The Department did not incur any Ffruitless and wasteful expenditure during the 4th Quarter of the 2020-2021 FY. - The Department did identify Ffruitless and wasteful expenditure amounting to R54 thousand during the 3rd Quarter of the 2020-2021 FY. The department did not pay a claim on demand in the matter of Official vs GDARD in terms of a settlement agreement between the parties regarding a labour dispute. The matter was litigated when GDARD’s HR Chief Director refused to honour the terms of the settlement agreement and in turn did not respond to the Sheriff of the Court’s Execution Notice because the Department disputes the outstanding claim. The Fruitless and wasteful expenditure incurred by the Department relates to storage costs incurred by the Sheriff of the Court when removing furniture form the Department to cover the claim. The claim was settled and a week later the furniture was returned. This case is currently under investigationed. - The Department did disclose Ffruitless and wasteful expenditure amounting to R6.5 million in the 2019-2020 Financial year, this investigation still needs to be finalised. The findings and recommendations in the Investigation Report will determine the effective and appropriate disciplinary steps against any employee who makes or permits fruitless and wasteful expenditure. - Irregular expenditure The Department received an Internal Audit Report which identified irregular expenditure for the 4th Quarter of the 2020-2021 FY. The Request for quotations (RFQ’s) were used for the procurement of office space instead of going through the competitive bidding process. The RFQ’s for the period under review for Randfontein Region amounted to R600 576.00 although the Department had already committed to pay an amount of R1 600 960.00 by end of December 2020. The Department however do have Irregular expenditure amounting to R86.1 million relating to the 2016-2017 and 2017-2018 Financial Yyear, most of these cases were investigated and the Department is in a process for implementing the findings and recommendations as indicated in the investigation report. The Provincial Forensic Audit unit within Gauteng office of the Premier (OOP) is in a process of finalising the rest of other investigations.

A summary for the period under review with respect to efficiency / value for money in all SCM / procurement processes

All tenders with the value above R2 million are processed through an open tender process and probity auditors are appointed to provide quality assurance on Terms of reference before being published and during evaluations. Further to that, The SCM infrastructure policy has been reviewed and an exception was provided in the policy for a deviation on procurement for infrastructure minor projects.

A summary for the period under review with respect to reduction of fraud and corruption in all SCM / procurement processes

None reported

A summary for the period under review with respect to ongoing clean audits

None for the quarter under review

A summary for the period under review with respect to spending on conditional grants (where applicable)

The department reported that they spent R124.2 million on grants of its R132.5 million adjusted budget that is equivalent to 94% of its budget allocation. - Comprehensive Agricultural Support Programme (CASP) has spent R96 million which is equivalent 96% of its allocated budget of R100.1 million and the under expenditure is on CASP ERP, R1.7 million rollover request was made on committed projects. - Illima/Letsema grant spent R25.4 million that is equivalent to 100% of its allocated budget. Budget was spent on supply of production inputs. - EPWP incentive grants spent R2.2 million that is equivalent to100% of budget allocated. This was spending on projects related to establishment of indigenous ornamental and food crop nurseries.

Program / Sub Programme level financial performance

The Department managed to spendt R289.3 million of its project Budget for the 4th quarter, that equals 87% of its budget. Administration (Programme 1) has spent R56,8 million of its adjusted budget that is equivalent to 96% of its budget allocation, Agriculture and Rural Development (Programme 2) has spent R100 million of its adjusted budget that is equivalent to 71% of its budget allocation Environmental Affairs (Programme 3) has spent R132.2 million of its adjusted budget that is equivalent to 1050% of its budget allocation.

# 5	OVERSIGHT ON DEPARTMENT / ENTITY RESOLUTIONS AND PETITIONS MANAGEMENT

| 5.1 THE DETAILS ON DEPARTMENT / ENTITY RESOLUTIONS MANAGEMENT |  |
| --- | --- |
| How many Responses / Actions to Resolutions were due by the Department / Entity during the Quarter under review | With respect to any and all Resolutions that were due in the Quarter under review, how many Resolutions have been successfully responded to by the Department / Entity |
| 22 responded to | 18 were adequately responded to |
| What is the Committees perception of the Quality and Timeliness of Department / Entity responses to Committee Resolutions |  |
| Acceptable – The Department is encouraged to continue improving on unachieved plans |  |
| With respect to the Resolutions / Action due during the Quarter under review but still overdue, what reasons have been provided by the Department / Entity [with mitigating measures to submission] |  |
| Resolutions were all submitted in the quarter under review |  |

| 5.2 THE DETAILS ON DEPARTMENT / ENTITY PETITIONS MANAGEMENT |  |
| --- | --- |
| How many Responses / Actions to Petitions due by the Department / Entity during the Quarter under review | With respect to any and all Petitions that were due in the Quarter under review, how many Petitions have been successfully responded to by the Department / Entity |
| 1 | 1 |
| What is the Committees perception of the Quality and Timeliness of Department / Entity responses to referred Petitions |  |
| N/A |  |
| With respect to the Petitions / Action due during the Quarter under review but not yet responded to by the Department / Entity, what reasons have been provided by the Department / Entity [with mitigating measures to submission] |  |
| N/A |  |

# 6	OVERSIGHT ON DEPARTMENT / ENTITY PUBLIC ENGAGEMENT

6. THE DETAILS ON DEPARTMENT / ENTITY PUBLIC ENGAGEMENTS

The steps / measures the Department / Entity has taken to meaningfully involve the public / stakeholders in the course of its work / service delivery, during the period under review

The Committee noted the following public engagements that the Department attended to: IGR Coordination Sub-Work stream engagements - The Department of Agriculture and Rural Development actively participated in the IGR Coordination Sub-Work stream engagements convened by COGTA to discuss the integrated Health Programme for the 5 (five) Districts including the vaccine roll out plan. - Through these engagements, the Department was actively involved in the Ward Based War Rooms as per drafted schedules by COGTA for the reporting period under review. Departmental Outcomes/ Steps to be undertaken towards service delivery - Integrated service delivery innovations as well as outline of role clarifications for different GPG Departments towards support of the Integrated Health Programme; - As part of IGR stakeholder engagements; the Department also held a joint IGR Strategic Planning Session with GDED towards overview of both the departmental Operational Plans on IGR matters; outline of key focus areas per corridor; as well as unpacking of processes and procedures towards the development of an integrated joint IGR Policy; - The steps undertaken in meaningfully engaging with DED included mapping way forward towards strengthening the capacity of municipalities to manage their own affairs, to exercise their powers and to perform their functions. MEC/MMC Joint Political IGR - An MEC/MMC Joint Political IGR was held with GDARD/DED and municipalities during the reporting period under review to discuss issues of mutual interest with Municipalities. Stakeholder Engagements: various stakeholder engagements transpired for the period (January-March 2021) as follows: - - Coordination of the School Reopening Program in conjunction with GDE in view of monitoring the Gauteng school’s readiness for the financial year 2021. This is in line with schools’ visits by all GPG MEC deployment by Gauteng Premier. - GDARD participated in symbolic tree planting; provision of seeds to the school; walkabouts to school programs as well as support to DSD by means of symbolic handover of dignity packs and school uniforms to identified learners; - Through the Bontle-Ke-Botho Clean-up Campaign Programme, the Department during the reporting period conducted a clean-up campaign as requested by the Ward Councillor in the Sharpeville area (Emfuleni Municipality). - The Department together with DED met with the Johannesburg Chamber of Commerce Industry (JCCI) to establish partnerships. - The MEC had stakeholder engagement with farmers at Hekpoort (Nonhle’s Farm) and during public participation focus was on the support for farmers through Departmental programmes as well as MEC’s introduction to the stakeholders. Challenges raised by the farmers were more related to issues around production inputs for small scale farmers as well as a need for self-sustainability. The Department committed to farmers on aspects in related to access to markets, which is currently posing a challenge; a need to relook at the pack houses concept as well as strengthening of major contributions to Agriculture and Agro-processing. - Departmental support to strengthen the existing programme on Agro-processing and Agriculture; GDARD also through the MEC’s stakeholder engagement met with WARD and YARD to address challenges raised by farmers which includes lack of access to markets, land audits; land rights and EIAs licensing. To address the triple challenges of poverty; unemployment and inequality, the department will look at critical indicators related to commercialization as well as harnessing of relations with local retailers.

Summary of Public Education programmes of the Department / Entity during the period under review

The Committee encourages the Department to continue collaborating with various Departments to strengthen the Ward Based Approach through IGR coordination as championed by COGTA. The Department through Public Education programmes in relation to COVID-19 was in a position to align its programmes in view of strengthening the Ward Based Approach, and as such integrated support with various Departments was realised during the period under review.

Feedback sessions conducted by the Department / Entity during the period under review

The Committee noted that the objective of the engagements were to introduce the MEC to the farmers, discuss their challenges, as well as providing suggested solutions and any new ideas in line with service delivery. Through the engagements held during the reporting period under review, the Department was well positioned in responding to all the cross-cutting issues as raised by farmers such as market access, EIA processes and training of farmers. The feedback sessions conducted by the Department during the reporting period under review outlined the following key areas towards effective and efficient service delivery aspects: - Implementation of government promises of transforming and improving Agriculture in the province;

# 7	OVERSIGHT ON INTERNATIONAL TREATISE / AGREEMENTS

7. DETAILS ON IMPLEMENTATION OF INTERNATIONAL AGREEMENTS / TREATIES [Applicable only to OCPOL / OoP]

[Enter information here]

# 8	OVERSIGHT ON DEPARTMENT / ENTITY GEYODI EMPOWERMENT

8. DETAILS ON DEPARTMENT / ENTITY GEYODI EMPOWERMENT

GENDER 22.19% of total procurement that targets businesses owned by Women. 56%of women employed at SMS level within the department. 28 women producers in community food gardens supported with production inputs. 7 women benefitted from Agri-parks. YOUTH 3.79% of total procurement that targets businesses owned by Youth. 1305 work opportunities created through Tshepo 1 million. 1 475 work opportunities were created through environmental programmes. DISABED 0.42% of total procurement that targets businesses owned by Persons with Disabilities (PwDs) 3% of people with disabilities employed within the Department. SENIOR CITIZENS – N/A

# 9	OVERSIGHT ON DEPARTMENT / ENTITY COMPLIANCE WITH FIDUCIARY REQUIREMENTS

| 9. [DETAILS ON DEPARTMENT / ENTITY COMPLIANCE WITH FIDUCIARY REQUIREMENTS] |  |
| --- | --- |
| GPL | The 4th Quarterly Report for Vote 11 was submitted to the GPL for further processing |
| Auditor General (AGSA) | None for the quarter under review |
| Public Service Commission (PSC) | None for the quarter under review |
| Compliance with relevant fiduciary Legislation [e.g. PFMA] | Compliant |

# 10	OVERSIGHT ON A CAPACITATED PUBLIC SERVICE

10. THE DETAILS ON A CAPACITATED DEPARTMENT / ENTITY

Detailed information on the current vacancies (at all staff levels)

1 059

Current vacancy rate

Current acting positions (at all Staff levels)

3

Terminations during the period under review

3

New appointments during the period under review

18

Detailed information on the GEYODI / HDI empowerment for the period under review

Total Females in the Department = 506 (52%), SMS Females = 22 (56%), PwD = 26 (2.7%)

Detailed information on any suspensions for the period under review

0

# 11	OVERSIGHT ON ANY OTHER COMMITTEE FOCUS AREA

11. THE DETAILS ON ANY OTHER COMMITTEE FOCUS AREA [Only if relevant and applicable]

Any other area of Department / Entity performance with respect to its Quarter Report that the Committee wishes to report on, which is not already included in any of the above Focus Areas.

N/A

# 12	COMMITTEE FINDINGS / CONCERNS

12. DETAILED COMMITTEE FINDINGS / CONCERNS (on each specific Focus Area analysed above)

With respect to [Irregular Expenditure], the Committee is concerned with the inability by the Department to implement recommendations by the Auditor General on irregular expenditure.

With respect to Consequence management], Lack of consequential management and accountability on targets not achieved.

With respect to Programme Performance, specifically Programme 2 & 3, the Committee is concerned with the failure to align its budget with its planned targets, as under expenditure is continuously observed in Agriculture and Rural Development and Environmental Affairs Programme.

With respect to [Project Management], the Committee is concerned with the Lack of completing capital funded projects and spending in goods and services due to tender processes that are being implemented through the open tender system.

# 13	COMMITTEE RECOMMENDATIONS

| 13 [DETAILED COMMITTEE RECOMMENDATIONS] |  |  |  |
| --- | --- | --- | --- |
| Based on the information set out herein-above as well as the Committee Concerns, the Committee therefore recommends as follows: |  |  |  |
| Ref Number | Recommendation | Type of response expected | Due Date |
| EDEARD /Q4PR/ 001 | Provide the Committee with a detailed report on how irregular expenditure and non-compliance will be prevented including measures in place. | Written Response should be forwarded to the GPL on the resolution as adopted by the House | 30/09/2021 |
| EDEARD/ Q4PR / 002 | Provide the Committee with a comprehensive report on consequential management for targets not met. | Written Response should be forwarded to the GPL on the resolution as adopted by the House | 30/09/2021 |
| EDEARD/ Q4PR / 003 | Department to provide monitoring and evaluation quarterly reports on the progress of how planned targets are achieved and the budget is spent on planned projects. | Written Response should be forwarded to the GPL on the resolution as adopted by the House | 30/09/2021 |
| EDEARD /Q4PR / 004 | Department to provide a feedback report/plan on how DBSA will implement capital funded projects and completion date. | Written Response should be forwarded to the GPL on the resolution as adopted by the House | 30/09/2021 |
| Explanatory note on the reference numbers for Recommendations (ultimately Resolutions) - Reference number is in the format : [A] / [B] / [C] - [A] = The 3 letter Committee identifier. E.g. COGTA/HS can be “CHS”, SRAC can be “SRA” - [B] = The 4 digit identifier for the SOM Imperative [e.g. Q1PR or Q2PR or FIS1 or APR, or BV. In this case, since this is a Q-Report template, it will either be Q1PR or Q2PR or Q3PR or Q4PR] - [C] = The 3 digit number of the recommendation in this report [001,002,003 …, 00n] |  |  |  |

# 14	ACKNOWLEDGEMENTS

The Portfolio Committee on Economic Development, Environment, Agriculture and Rural Development wishes to thank the MEC for Economic Development and Agriculture and Rural Development, Mr Parks Tau, the Head of Department, Ms M Gasela and her team of officials. The Chairperson, Ms L Lasindwa further wishes to acknowledge and express her gratitude to the Honourable Members of the Portfolio Committee on Economic Development, Environment, Agriculture and Rural Development Members Ms F Hassan,  Mr L Makhubela, Ms B Mncube, Mr M Gana, Ms A Cilliers, Mr A Tshitangano, Mr J Hoffman, Mr D Adams. Further appreciation goes to the alternate Members of the Committee namely Members:  Mr A Alberts, Ms Du Plessis and Ms B Badenhorst. It is an honour to lead such a hard-working team.Furthermore, the Portfolio Committee would like to express appreciation for the contribution of the following support staff members: Group Committee Coordinator Mr T Bodibe; the Committee Researchers Mr B Mabuza, Ms M Makhubele and Dr A Malapane, Senior Committee Coordinator Mr T Skosana, Committee Coordinator  Ms L Mampe, Administrative Assistants; Ms N. Mngadi and Ms V Mokubetsi, Hansard Recorder Mr S Baloyi, Senior Information officer, Ms Azwinndini Netshivhuyu, Communications Officer; Mr Takalani Ndou, Service Officer Ms Busisiwe Nhlapo, and Public Participation Officer: Mr B Dhlomo for their dedication and commitment.

# 15	ADOPTION

In terms of Rule 117 (2)(c) read together with 164, the Economic Development, Agriculture and Rural Development Portfolio Committee presents the Oversight Report on the 4th Quarterly Performance Report of the Gauteng Department of Agriculture and Rural Development for the 2020/21 financial year and recommends its adoption.