## Slide 1: GAUTENG DEPARTMENT OF SOCIAL DEVELOPMENT 2020/21 FY PERFORMANCE MONITORING REPORT: ANALYSIS OF PERFORMANCE
SOCIAL DEVELOPMENT PORTFOLIO COMMITTEE
12 November 2021

## Slide 2: Table Of Contents
  Part A: Overview Of Department Performance.
  Part B: 1. Non-financial Performance:
  2. Governance And Administration
  3. Areas of Significant Deviation from Planned Performance
  4. Monitoring of NPOs
  5. Extraordinary Issues
  Part C: Financial Report
2

## Slide 3: Purpose
To present Departmental performance for the 2020/21 FY.
3

## Slide 4: Non-financial performance report Technical analysis per programme/sub-programme
PART A
Overview of Department Performance
4

## Slide 5: Rating Categories
The performance for the Department is disaggregated according to the threshold represented by the following ratings categories and definitions:
Rating Symbol | Rating Category | Value
 | Achieved | 100% and greater
 | Not Achieved: Good progress | 76% - 99%
 | Not Achieved: Fair progress | 51% - 75%
 | Not Achieved: Poor Progress | 26% - 50%
 | Not Achieved: Very Poor Progress | Less than 26%
 | Not targeted for the Q | No quarterly targets set for the quarter under review.

## Slide 6: Overview Of Non-Financial Performance
Chart: 2020/2021 FY
| PROG 1: ADMINISTRATION | PROG 2: SOCIAL WELFARE SERVICES | PROG 3: CHILDREN AND FAMILIES | PROG 4: RESTORATIVE SERVICES | PROG 5: DEVELOPMENT AND RESEARCH | OVERALL PERFORMANCE
Achieved (100% and greater) | 0.6129 | 0.48 | 0.2963 | 0.82857 | 0.64706 | 0.59211
Good Progress (greater that 75% | 0.29032 | 0.28 | 0.14815 | 0.17143 | 0.14706 | 0.20395
Fair Progress (51% - 75%) | 0.064516 | 0.08 | 0.2963 | 0 | 0.11765 | 0.10526
Poor Progress (26% - 50%) | 0.032258 | 0.12 | 0.18519 | 0 | 0.029412 | 0.065789
Very Poor Progress (Less than 25%) | 0 | 0.04 | 0.074074 | 0 | 0.058824 | 0.032895
Not Targeted | 0 | 0 | 0 | 0 | 0 | 0
Notes: Overview comparison.

## Slide 7: Year On Year Comparison
Chart: Year On Year Comparison
| Prog 1: Administration | Prog 2: Social Welfare Services | Prog 3: Children and Families | Prog 4: Restorative Services | Prog 5: Development and Research | Overall Dept. Performance
17/18FY | 0.67 | 0.73 | 0.85 | 0.89 | 0.86 | 0.81
18/19 FY | 0.62 | 0.73 | 0.71 | 0.92 | 0.69 | 0.73
19/20FY | 0.69 | 0.76 | 0.68 | 0.83 | 0.58 | 0.71
20/21FY | 0.61 | 0.48 | 0.3 | 0.83 | 0.65 | 0.59

## Slide 8: Achievement vs Weighted Performance
Chart: Achievement vs Weighted Performance
| Annual Achievement | Weighted rating scale
2020/21FY | 0.59 | 0.85

## Slide 9: Non-Financial Vs Financial Comparison
Weighted YTD Non-Financial performance against YTD financial expenditure
Chart: Non-financial vs. Financial performance
| Overall Dept perfomance | Prog1 | Prog 2 | Prog 3 | Prog 4 | Prog 5
Non Financial performance(%) | 0.85 | 0.9 | 0.81 | 0.68 | 0.97 | 0.86
Financial Expenditure(%) | 0.93 | 0.95 | 0.98 | 0.88 | 0.98 | 0.93

## Slide 10: Provincial Priorities
Chart: Achievement of Provincial Strategic Priorities
| Priority 1: Economy, Jobs & Infrastructure | Priority 4: Safety, Social Cohesion and Food Security
Achieved (100% and greater) | 0.7 | 0.6
Good Progress (greater that 75% | 0.3 | 0.12
Fair Progress (51% - 75%) | 0 | 0.04
Poor Progress (26% - 50%) | 0 | 0.16
Very Poor Progress (Less than 25%) | 0 | 0.08
Not Targeted | 0 | 0

## Slide 11: National Priorities
Chart: Achievement of National Strategic Priorities
| Priority 2: Economic Transformation and Job Creation | Priority 4: Consolidating the social wage through reliable and quality basic services
Achieved (100% and greater) | 0.73333 | 0.54167
Good Progress (greater that 75% | 0.26667 | 0.16667
Fair Progress (51% - 75%) | 0 | 0.041667
Poor Progress (26% - 50%) | 0 | 0.16667
Very Poor Progress (Less than 25%) | 0 | 0.083333
Not Targeted | 0 | 0

## Slide 12: Departmental Achievement of National and Provincial Strategic Priorities
DEPARTMENT ACHIEVEMENT OF STRATEGIC PRIORITIES |  |  | 
STRATEGIC LINKAGES |  | STRATEGIC PLANNING | STRATEGIC REPORTING
NDP/MTSF Priority | GGT Priority | Outcome as per approved Dept Strategic Plan | Summarised Performance
Priority 2: Economic transformation and job creation | Priority 1: Economy, Jobs & Infrastructure | Reduce hunger and poverty | National Priority 2: of the 15 planned targets, 11 were fully achieved at 73% and 4 were partially achieved at 27% Provincial Priority 1: of the 10 planned targets, 7 (70%) indicators were fully achieved while 3 targets were partially achieved at 30%
Priority 4: Consolidating the social wage through reliable and quality basic services | Priority 4: Safety, Social Cohesion and Food Security | Enhanced care and protection of poor and vulnerable groups Reduce hunger and poverty Reduce the demand for substances and harm caused by substances | National Priority 4: Of the 24 planned targets, 13 were fully achieved at 54% and 4 (17%) were partially achieved, 1 on fair progress at 4%, with 4 targets (17%) on poor progress and 2 (8%) not being achieved Provincial Priority 4: Of the 25 planned targets, 15 were fully achieved at 60%, 3 were partially achieved at 12% and 1 on fair progress at 3%, with 4 targets (16%) on poor progress and 2 (8%) not being achieved

## Slide 13: 1. Programme Performance
Part B:
Non-financial Performance
13

## Slide 14: Overview Of Non-Financial Performance: Prog 2
Chart: Programme 2: Social Welfare Services
| 2.2 Services to Older Persons | 2.3 Services to the Persons with Disabilities | 2.4 HIV and AIDS | 2.5 Social Relief
Achieved (100% and greater) | 0.5 | 0.44444 | 0.57143 | 0
Good Progress (greater that 75% | 0.25 | 0.44444 | 0.14286 | 0
Fair Progress (51% - 75%) | 0 | 0.11111 | 0.14286 | 0
Poor Progress (26% - 50%) | 0.125 | 0 | 0.14286 | 1
Very Poor Progress (Less than 25%) | 0.125 | 0 | 0 | 0
Not Targeted | 0 | 0 | 0 | 0
Notes: Bar chart with sub programmes
See if we can include weighted avg within this slide along with bar chart.

## Slide 15: Care and Service to Older Persons
During the period under review :
17 436 (T:22 435) older persons were reached through services provided by funded community-based care and support facilities (home based; service centres and luncheon clubs) and 5 940 (T:6 581) older persons benefitted from residential facilities
Active ageing programmes reached 9 778 (T:20 415) older persons including gym facilities programmes.
202 240 (T: 61 204) beneficiaries were reached through elder abuse prevention programmes
15

## Slide 16: Care and Service to Older Persons
16
COVID-19 Interventions
Procurement of PPEs for residential facilities, home-based care and protective Workshops was completed in the 4th Quarter.
Training by Department of Health on Infection Control for nurses at residential facilities for older persons
Training of Nurses in residential facilities by the Department of Health on the vaccination programme commenced in March 2021 and is continuing.
Education and Awareness programmes
The International Day of Older Persons was celebrated through the publication of the Rights of Older Person on Facebook on 01/10/2020
As part of the continued elder abuse awareness raising, pamphlets on Elder Abuse were distributed at SASSA pension pay-points
Community Radio interviews to market services provided to Older Persons were also conducted

## Slide 17: Services to Persons with Disabilities
During the period under review the following were achieved:
  Education and awareness programmes on disability prevention reached 1 426 885 (T:62 337) beneficiaries.
  Residential and assisted living care were accessed by 1 861 (T:1 994) Persons with Disabilities in government and NPO managed facilities; 486 (T:491) benefitted from home-based care services
  Protective workshop programme aimed at socio economic empowerment of persons with disabilities reached 3 530 (T:4 476) beneficiaries.
  8 936 (T:14 906) persons with disabilities received psycho-social support services.
17

## Slide 18: Services to Persons with Disabilities
18
COVID-19 Interventions
Training by Department of Health on Infection Control for nurses at residential facilities for persons with disabilities regionally.
COVID-19 compliance audits conducted together with Department of Health at 37 residential facilities for persons with disabilities from 11 – 20 August 2020
Procurement of PPEs for residential facilities, home based care and protective workshops was completed in the 4th Quarter.
Training of Nurses in residential facilities by the Department of Health on the vaccination programme commenced in March 2021 and is continuing.
Education and Awareness programmes
Radio interviews in relation to Mental Health related issues for Social Development Month as well as COVID 19 related matters were conducted by regional coordinators between 13 – 20 October 2020 in all the regions.
In total,11 Radio interviews in relation to DRAM 2020 as well as COVID 19 related matters were conducted by regional coordinators between 09 – 30 November 2020.
As part of DRAM 2020 and COVID 19 awareness raising, 6 SASSA Pay points were visited to distribute promotional material in West Rand, Tshwane and Sedibeng Regions on 4 November 2020 reaching an estimated 2 555 Persons with disabilities and 4 SASSA pay points on 02 December 2020 in the Sedibeng Region reaching an estimated 1719 persons with disabilities.

## Slide 19: HIV And AIDS & EPWP
During the period under review the following were achieved:
Nutritional support was provided to 235 292 (T:117 680) through food parcels and 15 385(T:37 900) through cooked meals
71 304 (T:99 477) beneficiaries received psychosocial support services including Orphans and Vulnerable Children
181 548 (T:137 624) beneficiaries were reached through the Social behaviour Change Programmes
7 154 (T:7 210) work opportunities were created through EPWP
19

## Slide 20: HIV And AIDS & EPWP
20
During the period under review:
Prevention Programme
44 organisations were recommended and funded for the implementation of the Social and Behaviour Change Programme
G2G Programme – The process of appointing organisations that will implement the G2G programme was finalised.
Care and Support Program
A comprehensive package of essential services that include nutritional support, counseling, skills development, home and school visits, psychosocial support, educational support, medical support, food supplements and referrals was provided to:
- Orphans and Vulnerable Children and Youth (OVCY)
- Child and Youth Headed Households
- Older Persons who are caregivers and Support Groups

## Slide 21: Overview Of Non-Financial Performance: Prog 3
Chart: Programme 3: Children and Families
| 3.2 Care and Services to Families | 3.3 Child Care and Protection | 3.4 ECD and Partial Care | 3.5 Child and Youth Care Centres | 3.6 Community-Based Care Services for children
Achieved (100% and greater) | 0.28571 | 0.25 | 0.27273 | 0.66667 | 0
Good Progress (greater that 75% | 0.14286 | 0 | 0.18182 | 0 | 0.5
Fair Progress (51% - 75%) | 0.57143 | 0.5 | 0.090909 | 0 | 0.5
Poor Progress (26% - 50%) | 0 | 0.25 | 0.27273 | 0.33333 | 0
Very Poor Progress (Less than 25%) | 0 | 0 | 0.18182 | 0 | 0
Not Targeted | 0 | 0 | 0 | 0 | 0

## Slide 22: Care And Support To Families
During the period under review the following was achieved to ensure families perform the critical role of nurturing and caring for individual family members:
  114 720 (T:96 822) family members participated in preservation programmes
  4 920 (T:7 042) families participated in re-unification programmes
  1 646 (T:1 055) family members were reunited with their families
  40 812 (T:25 265) families participated in parenting programmes
  24 768 (T:32 389) families received crisis intervention services
22

## Slide 23: Care and Support to Families
23
During the period under review:
A service delivery campaign/ blitz was undertaken during September led by the MEC; with the aim of strengthening support services to the homeless. The following were achieved :
Profiling of homeless people
Strengthening of Partnerships with Departments /Stakeholders to promote intersectoral approach in dealing with homelessness
Development of plans to improve the management of the shelters
R 88 000 000.00 was received from Treasury. Business plans were submitted in consultation with the Municipalities in all regions. The rationalisation process will reduce the number of shelters from 42 to 24 (affected beneficiaries will be moved to other shelters and/or be re-integrated with their families). This will enhance effective management, habitability, improve services in current shelters and reduce operational costs.
Graduation Ceremony was hosted by the Department on 21 November for former homeless people and former substance abuse beneficiaries who were trained during the Lockdown on artisan skills.
11 homeless beneficiaries enrolled for the training and 5 completed. 3 were traced to attend the event, 1 is already working in KZN

## Slide 24: Child Care And Protection
24
During the period under review:
1 277 (T:1 790) ECD centres have been fully registered and
623 (T: 615) have been conditionally registered
50 415 (T:111 253) children accessed funded and non-centre based ECDs; 7 619 (T:17 688) children accessed conditionally funded ECDs
2 034 (T:5 022) children in need of care and protection were placed in foster care
38 691 (T:62 503) children already in foster care received social work services
4 141 (T:4 718) children were placed in CYCCs for developmental social welfare services.

## Slide 25: Child Care And Protection
25
During the period under review:
A workshop was held with Municipalities on their role in relation to the Children’s Act 38 of 2005, focusing on Partial Care Facilities and ECD Programmes.
A meeting was held with the Tshwane Municipality to discuss the blockages as experienced by the ECDs due to the Municipal By-Laws that were implemented retrospectively.
The Department in collaboration with NDSD hosted the closing of the Child Protection Week at Polokong Child and Youth Care Centre in Sedibeng Region, on the 07 June 2020, the theme was “Child Protection and Beyond”
The Province’s Child Ambassador joined the Minister and participated in the virtual discussion on the effects of COVID-19 on children on the 01June 2020.
3 250 ECD Practitioners were capacitated on the Standard Operating Procedures to curb the spread of Covid-19. PPEs were procured and distributed to qualifying ECDs.
A meeting was held on ECD Function Migration (from DSD to DBE) with National & Provincial Department of Social Development, National and Provincial Department of Education. The aim was to do role clarification and appointment of work-stream members
The report on Foster Care Programme was submitted to the North Gauteng High Court ,Centre for child Law, in November 2020 and to the Parliamentary Portfolio Committee, in October 2020. The North Gauteng High Court has extended the Court Order declaring all lapsed foster care orders up to date, November 2020.

## Slide 26: Overview Of Non-Financial Performance: Prog 4
Chart: Programme 4: Restorative Services
| 4.2 Crime Prevention and support | 4.3 Victim empowerment | 4.4 Substance Abuse, Prevention and Rehabilitation
Achieved (100% and greater) | 1 | 0.875 | 0.66667
Good Progress (greater that 75% | 0 | 0.125 | 0.33333
Fair Progress (51% - 75%) | 0 | 0 | 0
Poor Progress (26% - 50%) | 0 | 0 | 0
Very Poor Progress (Less than 25%) | 0 | 0 | 0
Not Targeted | 0 | 0 | 0

## Slide 27: Crime Prevention and Support
During the period under review the following were achieved:
Social crime prevention and awareness campaigns reached 1 292 351
(T:307 534) children and adults
All children and adults in conflict with the law referred to the Department for further interventions were attended to:
  4 026 (T:7 401) children and adults were assessed; 553 (T:1 298) were referred and 634 (T:2 129) participated in diversion programmes.
  2 secure care centers managed by government accommodated 608 (T:680) children in conflict with the law that are awaiting trial.
27

## Slide 28: Crime Prevention and Support
28
During the period under review
Capacity building was conducted for the following:
  Officials from secure care centers and Regions were trained on Bright Star program
  Minimum Norms and Standards for Diversion services
  Probation Case Management system and Child and Youth Application system
  Reintegration and Aftercare strategy
  Accreditation of Diversion Services system(ADS)
30 officials that were transferred from Father Smangaliso Mkhatshwa CYCC to Soshanguve secure care centre were trained on the Blueprint Minimum Norms and Standards for secure care facilities
Anti-Bullying summit was conducted in collaboration with stakeholders in the JCPS cluster

## Slide 29: Victim Empowerment
During the period under review the following were achieved:
The Department continues to create awareness against gender-based violence (GBV). On the 25th of each month awareness is created around Orange Day.
The Department funded 110 (T:101) facilities and shelters that provided psycho-social support to 44 153 (T:45 089) victims of violence and crime
The programme of no violence against women and children including 16 days of activism reached 437 895 (T:293 886) beneficiaries.
29

## Slide 30: Victim Empowerment
30
During the reporting period
Meeting with faith-based organisations in Sedibeng took place in view of the launch of Asikhulume by the National Minister of DSD
Provincial DSD hosted the DSD National minister’s events commemorating Human Rights Day in March 2021 at Mary Fitzgerald Square and Diepsloot
Capacity building was conducted for the following:
Trafficking in Person training
GBV training
Program for Intimate partner Violence
Isiqalo training
Governance training was offered board members of NPOs

## Slide 31: Substance Abuse Prevention and Rehabilitation
During the period under review
The Department continued to render substance abuse prevention and rehabilitation services in terms of the Prevention of and Treatment of Drug Dependency Act 70 of 2008 and the National Drug Master Plan to ensure that the demand and the harm caused by drugs is reduced.
1 640 244 (T:838 718) beneficiaries were reached through substance abuse prevention programmes
The Ke-Moja coaches deployed in schools and communities to roll out the Ke-Moja Drug Prevention programme reached 916 894 (T:860 179) children and youth.
Substance abuse disorder treatment services were provided to 22 360 (T:25 764) users.
  5 458 (T: 10 106) beneficiaries that completed treatment programmes are participating in after care programmes
31

## Slide 32: Substance Abuse Prevention and Rehabilitation
32
During the period under review:
The approved Gauteng City Region Anti-Substance Strategy, was formally launched by the MEC on 22 October 2020
Commemorated the International Overdose Awareness day which was hosted in collaboration with National Department of Social Development at Esidimeni Recovery Centre, Witpoort on the 31 August 2020
Commemorated World Foetal Alcohol Spectrum Disorders day on the 09 September 2020 in Orange Farm and at the Cosmo City Multi-purpose centre in collaboration with National Department of Social Department.
The department embarked on province wide media campaign at community radio stations to educate communities about dangers of substance abuse
21 Professional Nurses from Treatment Centres were trained on Covid-19 to ensure compliance to Covid-19 Lockdown Regulations
The department conducted training and capacity building programmes to ensure effective and efficient service delivery as follows:
Registration of treatment centres, halfway houses and services
10 inpatient treatment centres, 10 outpatient services, 27 Community Based services and 5 halfway house were registered in terms of the Prevention of and Treatment for Substance Abuse Act 70 of 2008.The department launched 3 mobile outpatient treatment services that operates in Sedibeng, West Rand and Johannesburg regions.

## Slide 33: Overview Of Non-Financial Performance: Prog 5
Chart: Programme 5: Development and Research
| 5.2 Community Mobilisation | 5.3 Institutional capacity building and support for NPOs | 5.4 Poverty Alleviation and Sustainable Livelihoods | 5.5 Community Based Research and Planning | 5.6 Youth development | 5.7 Women development | 5.8 Population Policy Promotion
Achieved (100% and greater) | 0.5 | 0.5 | 0.6 | 0.33333 | 0.85714 | 1 | 0.66667
Good Progress (greater that 75% | 0 | 0.25 | 0.2 | 0.33333 | 0.14286 | 0 | 0
Fair Progress (51% - 75%) | 0 | 0.25 | 0 | 0.33333 | 0 | 0 | 0.33333
Poor Progress (26% - 50%) | 0 | 0 | 0.1 | 0 | 0 | 0 | 0
Very Poor Progress (Less than 25%) | 0.5 | 0 | 0.1 | 0 | 0 | 0 | 0
Not Targeted | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 34: Poverty Alleviation And Sustainable Livelihoods
The Department through its funded organisations has:
  Poverty reduction programmes were accessed by 2 691 464(T:3 211 830) beneficiaries
  Distributed 548 998 (T:1 336 896) dignity packs.
  Enabled the participation of 56 825 (T:45 144) people in income generation programmes
  Distributed 1 760 458 (T:1 477 974) food parcels through foodbanks and
  41 023 (T:12 190) persons received food through feeding programmes.
  14 586 (T:14 538) beneficiaries participated in the Welfare to work programme
  545 (T:468) cooperatives provide goods and services to the Department
34

## Slide 35: Poverty Alleviation And Sustainable Livelihoods
The Department through its funded organisations has:
The provision of Dignity Packs and Food Parcels was declared as one of the services that the Department will champion during the COVID-19 lockdown to needy people. This includes donations from sourced partners.
Food Distribution was higher than APP targets to mitigate against the need for food during the national lockdown.
The gradual phasing of the reopening of schools limited the distribution of dignity packs.
The implementation of development programmes gradually started as per the Covid19 lockdown levels directives.
35

## Slide 36: Youth Development
During the period under review the following were achieved:
46 920 (T:33 299) work opportunities for youth have been created through the Youth Structures Programme EPWP and Job Centre Programme.
The programme has further enabled 55 092 (T:45 087) youth to participate in various skills development programmes through youth structures.
17 561 (T:17 836) youth participated in the Entrepreneurship Development Programme.
36

## Slide 37: Women Development
During the period under review the following were achieved:
The Department established partnerships with various training institutions, development agencies, the private sector and other government agencies to train women in skills such as financial management, marketing, business development and procurement procedures
20 755 (T:20 674) women participated in empowerment programmes
5 432 (T:5 200) women on child support grant were linked to economic opportunities
37

## Slide 38: Projects Completed During The Financial Year
PROJECT NAME | PROJECT DESCRIPTION | REGION | CONSTRUCTION PROGRESS | STATUS
Garankuwa Office Accommodation | Construction of Regional Office facilities | Northern Corridor | 100% complete. Office accommodation to alleviate shortage of space | 100% completed
Devon Early Childhood Development | Construction of Early Childhood Development Centre, | South Corridor | 100% complete. Alleviate shortage of space for Early Childhood development | 100% completed

## Slide 39: Projects Still Under Construction From Previous Years
PROJECT NAME | PROJECT DESCRIPTION | REGION | CONSTRUCTION PROGRESS | STATUS
Bekkersdal Social Integrated Facility | Construction of Early Childhood Development Centre, Day Care for Older Persons & Regional Office facilities | Western corridor | 77% complete. At superstructure level; the contractor is about to commence with landscaping and the perimeter fence. | 77% (Stage 5)
Bantubonke, Early Childhood Development Centre | Construction of Early Childhood Development Centre | Southern Corridor | 46% complete. Project experienced delays in approval of drawings by the municipality. The implementing agent submitted the application in terms of section 7 (6) and the municipality has now approved it. Contractor has now resumed with site works. | 46% (Stage 5)

## Slide 40: Human Resource Capacity
HUMAN RESOURCE CAPACITY: HUMAN RESOURCE MANAGEMENT |  |  |  | 
During the period under review 01 April 2020 to 31 March 2021 |  |  |  | 
Total number of posts on the Dept. Structure as at the last day of the period under review | Total number of posts currently filled as at the last day of the period under review | Total number of vacant posts as at the last day of period under review | Total number of vacant posts as at the last day of period under review | 
5 367 | 4 718 | 752 | 649 | 
Total number of acting positions as at the last day of the period under review | Total number of terminations during the period under review | Total number of new appointments during the period under review | Total number of new appointments during the period under review | 
5 | 322 | 71 | 285 | 
Total number of suspensions during the period under review | Summarized information on the GEYODI / HDI compliance for the period under review |  |  | 
1 |  |  |  | 
No employee placed on precautionary suspension for the period under review. | Females = 75.96% (3584 out of 4718) Youth = 38.13% (1799 out of 4718) Persons with disabilities= 2.75% (130 out of 4718) Race |  |  | 
1 |  |  |  | 
African | Coloured | Indian |  | White
95.10% (4 487 out of 4 718) | 2.33 % (110 out of 4718) | 0.42 % (20 out of 4718) |  | 2.14% (101 out of 4718)

## Slide 41: 2. Governance/ Administration
Part B:
Non-financial Performance
41

## Slide 42: Resolution Management
Resolution No. | Subject | Details | Response by the Department | Resolved (Yes/No)
 | Provide a strategy that seeks to minimise lawsuits before they materialise | The Department must provide the Committee with a strategy that seeks to minimise lawsuits before they materialise and a progress report detailing the effectiveness of measures put in place to address weaknesses in minimising lawsuits, every quarter and continuing up until the end of June 2020. | Legal Services has developed a contingency strategy for rolling out awareness sessions and legislative audits through alternative means such as video recordings, Skype, Microsoft Teams and any other available means in order to curb the increase in litigation. Legal Services is writing two articles per quarter to raise awareness amongst officials on legal matters and to ensure compliance with legislation. Matters that can be settled will be settled, instead of defending them in open court. We have written to the State Attorney to ensure that all matters that are dormant are dismissed by the courts. | Yes
2. | Preliminary SCOPA Resolutions | Fruitless and wasteful expenditure; litigation matters; irregular expenditure and investigations within the Department | The fruitless expenditure arose from the overpayment of two school uniform production co-operatives. These overpayments have since been transferred to debtors and the co-operatives have signed acknowledgements of debt. | Yes

## Slide 43: Governance/ Administration
ECD centre compliance
The registration of (ECD) centres is still a challenge due to municipal by-laws such as building plans, health certificates, and other infrastructural requirements. The Department is currently providing support to affected ECD centres so that they can meet the registration requirements.
Foster care backlog
Performance on foster care placements was hampered by compliance with lockdown regulations. The relevant psychologist and psychiatric services reports could not be acquired from the DoH and NDSD, nor could the relevant legal documents be obtained from prospective foster parents for submission to courts. The achievement of this target is also dependent on the courts. The Department will continuously monitor the foster care implementation plan, which includes engagements with the NDSD and other stakeholders.
Delay in provision of dignity packs and school uniforms
Performance here was affected by a delay in procurement after awarded contracts were withdrawn based on legal opinion, and SCM processes had to be followed. Performance on the distribution of school uniforms was further hampered by delays in payments to co-operatives and the delayed opening of schools as a result of COVID-19.

## Slide 44: 3. Areas of Significant Deviation from Planned Performance
Part B:
Non-financial Performance
44

## Slide 45: Indicators Showing Performance Below 80%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of older persons accessing community-based care and support services | 22 435 | 17 436 | Target: Not Achieved Performance is due to fewer beneficiaries accessing community-based care and support services than anticipated due to compliance to COVID-19 protocols. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 78%
Number of persons with disabilities accessing services in protective workshops | 4 476 | 3 530 | Target: Not Achieved Performance is due to fewer beneficiaries accessing services in protective workshops than anticipated due to compliance to COVID-19 protocols. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 79%
Number of vulnerable households receiving psychosocial support services | 40 300 | 31 646 | Target: Not Achieved Performance is due to limited access to communities as a result of COVID 19 regulations. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 79%

## Slide 46: Indicators Showing Performance Below 80%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of families receiving crisis intervention services (social work services) | 32 389 | 24 768 | Target: Not Achieved Performance is due to fewer beneficiaries participating in the programme than anticipated due to compliance to COVID-19 protocols. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 76%
Number of service users who accessed funded substance abuse community-based services | 12 227 | 9 380 | Target: Not Achieved All service users who reported and referred for treatment were admitted in the programme. The Lockdown Regulation impacted on the implementation of the community-based services. | The Department will continue to facilitate access to the programme. | 77%

## Slide 47: Indicators Showing Performance Below 75%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Vacancy rate of staff on salary level 13-16(%) | 10% | 18% | Target: Not Achieved SMS Posts filled in line with the post filling plan. Vacant SMS posts have been advertised. | The Department is currently monitoring the implementation of the post filling plan. | 56%
Percentage of persons with disabilities(PWD) employed by the Department | 4% | 3% | Target: Not Achieved Four (4) employees with disabilities resigned during the second quarter. | Disclosure of disability status by employees to be encouraged. Advertised posts to be filled in line with EE targets | 75%
Number of persons with disabilities receiving psychosocial support services | 14 906 | 8 936 | Target: Not Achieved Performance is due to fewer beneficiaries receiving psychosocial support services than anticipated due to compliance to COVID-19 protocols. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 60%

## Slide 48: Indicators Showing Performance Below 75%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of beneficiaries receiving Psychosocial Support Services (HCBC) | 99 477 | 71 304 | Target: Not Achieved Performance is due to limited access to communities as a result of COVID 19 regulations. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 72%
Number of families participating in re-unification programmes by Government | 2 993 | 2 124 | Target: Not Achieved. Performance is due to fewer families participating in re-unification programme due to compliance to COVID-19 protocols. Performance is further influenced by severity of family dysfunctionality and willingness to accept the family members | The Department will continue to provide the service to beneficiaries that present for the service in compliance with the current COVID-19 protocols.. | 72%
Number of families participating in re-unification programmes by funded NPOs | 4 109 | 2 796 | Target: Not Achieved Performance is due to fewer beneficiaries participating in the programme than anticipated due to compliance to COVID-19 protocols. Performance is further influenced by severity of family dysfunctionality and willingness to accept the family members. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 68%

## Slide 49: Indicators Showing Performance Below 75%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of families participating in parenting programmes | 40 812 | 25 265 | Target: Not Achieved Performance is due to fewer beneficiaries participating in the programme than anticipated due to compliance to COVID-19 protocols. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 62%
Number of family members reunited with their families | 1 646 | 1 055 | Target: Not Achieved Performance is due to fewer beneficiaries participating in the programme than anticipated due to compliance to COVID-19 protocols. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 64%
Number of children placed in foster care that receive social work services | 62 503 | 38 691 | Target: Not Achieved Performance was impacted by COVID 19 Lockdown restrictions as per Disaster Management Act (DMA) and regulations. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 62%

## Slide 50: Indicators Showing Performance Below 75%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number children in need of care and protection receiving psychosocial support services | 93 633 | 69 886 | Target: Not Achieved Performance was impacted by COVID 19 Lockdown restrictions as per Disaster Management Act (DMA) and regulations. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 75%
Number of fully registered ECD centres | 1 790 | 1 277 | Target: Not Achieved Performance was impacted by lockdown restrictions as per DMA regulation to curb the spread of COVID-19. ECDS not able to meet the minimum norms and standards as per Children's Act 38 of 2005. | The Department will continue to implement the ECD massification strategy; and monitor compliance to SOPs as per the objectives of Vangasali campaign. | 71%
Number of children reached through community-based prevention and early intervention programmes | 19 473 | 12 124 | Target: Not Achieved Performance is due to fewer beneficiaries participating in the programme than anticipated due to compliance to COVID-19 protocols. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 62%

## Slide 51: Indicators Showing Performance Below 75%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of NPOs capacitated | 500 | 368 | Target: Not Achieved Performance as a result of adherence to Lockdown Regulations, and poor attendance by the NPOs that were invited. | The Department will continue to facilitate access to the programme. | 74%
Number of households profiled | 16 000 | 11 471 | Target: Not Achieved Performance was impacted by COVID 19 regulations. | The Department will continue to support the programme. | 72%
Number of Population Advocacy, Information, Education and Communication (IEC) activities implemented | 11 | 8 | Target: Not Achieved Performance is due to delay in finalising the IEC action plan. | The Department will ensure that the action plan for the next financial year is realised. | 73%
Number of individuals who participated in population capacity building sessions | 85 | 63 | Target: Not Achieved Performance was hindered by COVID-19 restriction on gatherings as the nature of the indicator require direct contact through training | The Department will continue to provide capacity building sessions. | 74%

## Slide 52: Indicators Showing Performance Below 50%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of ECD centres maintained/ upgraded | 50 | 20 | Target: Not Achieved The conditional assessment took longer than anticipated and this has resulted in delaying submission of the specification to procurement. | It is envisaged that the remaining 30 ECD will be completed during the quarter 1 of 2021/22 financial year. | 40%
Number of older persons participating in active aging programmes | 20 145 | 9 778 | Target: Not Achieved Performance is due to fewer beneficiaries participating in active aging programmes than anticipated due to compliance to COVID-19 protocols. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 48%

## Slide 53: Indicators Showing Performance Below 50%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of beneficiaries receiving daily meals at HCBC organisations | 37 900 | 15 385 | Target: Not Achieved Performance is due to limited access to communities as a result of COVID 19 regulations. Comment: It should be noted that most of the beneficiaries were provided with food parcels as a mitigation mechanism. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 41%
Number of social relief applications recommended for approval by SASSA | 3 889 | 1 033 | Target: Not Achieved Performance is based on the beneficiaries eligible for social relief. Fewer social relief applications were recommended for approval due to compliance to COVID19 protocols. Furthermore, to be noted, SASSA focussed more on COVID related grants than SRDs | The Department will continue to facilitate access to the programme. | 27%
Number of children awaiting foster care placement | 1 064 | 453 | Target: Not Achieved Performance is due to compliance with Lockdown regulations and inability to acquire relevant reports from Psychologist & Psychiatric services from DoH, NDSD, as well as relevant legal documents from prospective foster parents for submission to Courts. | The Department will continue to monitor the implementation of foster care management plan and comply with the provision of North Gauteng High Court Order of 2019. | 43%

## Slide 54: Indicators Showing Performance Below 50%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of children subsidised through equitable share | 109 351 | 49 944 | Target: Not Achieved Performance was impacted by COVID 19 Lockdown restrictions as per Disaster Management Act (DMA) and regulations. ECDs are required to comply with specified health and safety directives before they can be allowed to operate. | The Department will continue to implement the ECD massification strategy; and monitor compliance to SOPs as per the objectives of Vangasali campaign. Comment: Deviation of funds was approved for ECDs to procure PPEs to ensure compliance to COVID 19 health and safety regulations. | 46%
Number of children subsidised through conditional grant | 17 688 | 7 619 | Target: Not Achieved Performance was impacted by COVID 19 Lockdown restrictions as per Disaster Management Act (DMA) and regulations. ECDs are required to comply with specified health and safety directives before they can be allowed to operate. | The Department will continue to implement the ECD massification strategy; and monitor compliance to SOPs as per the objectives of Vangasali campaign. Comment: Deviation of funds was approved for ECDs to procure PPEs to ensure compliance to COVID 19 health and safety regulations. | 43%

## Slide 55: Indicators Showing Performance Below 50%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of children with disabilities accessing registered ECD programmes | 282 | 103 | Target: Not Achieved Performance is attributed to COVID 19 ECDs related protocols which required ECDs to comply with specified health and safety directives before they can be allowed to operate. | The Department will continue to implement the ECD massification strategy and monitor compliance to SOPs as per the objectives of Vangasali campaign. | 37%
Number of child and youth care centres (CYCC) capacitated to meet compliance with transformation in line with the norms and standards of the Children’s Act | 119 | 38 | Target: Not Achieved Performance was impacted by lockdown restrictions as per DMA regulation to curb the spread of COVID-19 | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 32%
Number of dignity packs distributed | 1 336 896 | 548 998 | Target: Not Achieved Performance is due to a delay in the procurement of dignity packs, inter alia because of the withdrawal of awarded contracts following legal opinion and subsequent SCM processes that had to be followed. | Distribution of dignity packs as awarded will continue in the next financial year. | 41%

## Slide 56: Indicators Showing Performance Below 25%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of older persons in 50 poorest wards and other prioritised areas utilising gym facilities | 3 237 | 236 | Target: Not Achieved Performance is due to fewer beneficiaries accessing community-based care and support services than anticipated due to compliance with COVID-19 protocols. | The Department will continue to facilitate access to the programme in compliance with the current COVID-19 protocols. | 7%
Percentage of newly funded partial care sites (ECDs) managed by funded NPOs | 50 | 0 | Target: Not Achieved Comment: Performance was impacted by COVID 19 Lockdown restrictions as per Disaster Management Act (DMA) and regulations. Identified ECDs were e required to comply with specified health and safety directives before they can be allowed to operate. | The Department will continue to provide capacity building to NPOs to meeting compliance (funding requirements). | 0%

## Slide 57: Indicators Showing Performance Below 25%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Number of children accessing non-centre based services | 1 902 | 471 | Target: Not Achieved Performance was impacted by COVID 19 Lockdown restrictions as per Disaster Management Act (DMA) and regulations. ECDs are required to comply with specified health and safety directives before they can be allowed to operate. | The Department will continue to implement the ECD massification strategy; and monitor compliance to SOPs as per the objectives of Vangasali campaign. | 25%

## Slide 58: Indicators Showing Performance Below 25%
Performance Indicator | 2020/21 Target | 2020/21 Actual | Reason for Deviation | Mitigating measure | % Achieved
Percentage of Ntirhisano commitments achieved | 100% | 0% | Target: Not Achieved Performance on Ntirhisano was affected due to Lockdown restrictions. | The Department will await guidance from OoP on when Ntirhisano activities will be conducted. | 0%
Number of school uniform packs distributed | 169 500 | 11 498 | Target: Not Achieved Performance is due to delays in the payments to cooperatives have affected the readiness of cooperatives to distribute uniforms when schools re-opened. Performance was further affected by delayed opening of schools as a result of COVID19. | The Department is currently tracking payments to cooperatives on a weekly basis. The Department will further continue with distribution in the next financial year. | 7%

## Slide 59: 4. Monitoring Of NPOs
Part B:
Non-financial Performance
59

## Slide 60: Monitoring Of NPOs
In the period under review the Department funded 2 743 NPOs to render a variety of social welfare and developmental services.
The Department capacitated 368 (T:1 606) NPOs

## Slide 61: 5. Extraordinary Issues
Part B:
Non-financial Performance
61

## Slide 62
Extraordinary Issues
The Department participated in Special M&E Forum to discuss the new GPL Standardised Oversight, Accountability and Reporting (SOAR )template for Gauteng Province that was rolled out in the 2nd Quarter 2020/21 financial year.
The Department Performance Information Coordinating Committee (PICC) HOD and MEC Quarterly Review sessions were conducted virtually through Microsoft teams with Programme managers and Executive Management in compliance with Lockdown directive on Covid-19.

## Slide 63: Key Success Stories
SUB-PROGRAMME | KEY SUCCESSES
Child Care and Protection | The Province’s Child Ambassador joined the Minister and participated in a virtual discussion on the effects of COVID-19 on children on the 01st June 2020. The Department, in collaboration with the NDSD, hosted the closing of Child Protection Week at Polokong Child and Youth Care Centre in Sedibeng Region, on the 07th June 2020. The theme was “Child Protection Beyond”.
Services to Persons with Disabilities | The training of nurses in residential facilities by the Department of Health on the vaccination programme commenced in March 2021 and is continuing. Virtual training on the Guideline on service to children with disabilities in the Gauteng Province took place on the 02nd of March 2021 and was attended by 71 persons.
HIV and AIDS | For implementation, the Social and Behaviour Change Programme was handed over to the province by the Deputy Minister, Ms H Bogopane Zulu. The National Department of Social Development was assisted with the selection process for the implementation of the Government to Government (G2G) programme. Calls for proposals went out for the implementation of the G2G programme (YOLO and Chommy). For the implementation of the Social and Behaviour Change Programme, 44 organisations were recommended and funded.
Child Care | Gauteng Department of Social Development acknowledged the excellent performance of a hundred (100) top foster care grant beneficiaries who wrote their matric in 2020.

## Slide 64: Key Success Stories
SUB-PROGRAMME | KEY SUCCESSES
Victim Empowerment | On the 21st of November 2021, a graduation ceremony was hosted by the Department for ex-homeless people and ex-substance abuse beneficiaries who had been trained during the lockdown in artisan skills. On the 26th of November 2020, promotional material was distributed at a Department of Community Safety: Disability and Gender Based Violence event held at Birchwood Hotel in Boksburg in the Ekurhuleni as well as on the 03rd of December 2020 at the Cloverdale Mall in Benoni as part of the DSD Services Blitz in the Ekurhuleni Region. Gauteng Department of Social Development in partnership with Moving Ahead Development Agency (MADA) hosted the third memorial lecture on gender – based violence. The engagements was aimed at creating awareness on issues of gender-based violence (GBV) and Femicide. As part of 16 days of activism for no violence against women and children, the Department of Social Development (DSD) hosted a dialogue with Interfaith/Religious Sectors in Sedibeng, tackling issues of Gender-Based Violence and Femicide (GBVF) in the area.
Crime Prevention and Support | An anti-bullying summit was conducted in collaboration with stakeholders in the JCPS cluster on the 10th of March 2021. Seventy (70) officials from secure care centres and regions were trained on the Bright Star programme on 12-14th October and 9th -12th November 2020. On the 25th of November 2020, fifty (50) officials were trained on minimum norms and standards for diversion services. On the 7th -11th of December 2020, eighty (80) officials were trained on probation case management system and the child and youth application system.
Substance Abuse Prevention and Rehabilitation | The Department commemorated International Overdose Awareness day, which was hosted in collaboration with the National Department of Social Development at Esidimeni Recovery Centre, Witpoort on the 31st of August 2020. World Foetal Alcohol Spectrum Disorders day was commemorated on the 9th of September 2020 at Orange Farm in collaboration with National Department of Social Department and at Cosmo City Multi-Purpose Centre.

## Slide 65: Key Success Stories
 | KEY SUCCESSES
Sustainable Livelihoods | On 15 April 2020 acting MEC for Social Development Panyaza Lesufi received and welcomed food donations worth R2,5 Million. These donations prioritized the vulnerable and support families in distress amid the Covid – 19 outbreak.
Care and Support to Families | 483 homeless people were reintegrated after 2 752 were taken off the streets and placed in 45 city shelters when the pandemic hit. Temporary shelters provided psychosocial support, medical assessments and treatment for substance abuse
Administration | Ethics Management Committee (EMC) held a three days meeting with Non-Profit Organisations, to bring to their attention, their role in fighting fraud and corruption; creating an ethical environment and promoting ethical conduct.
Youth Development | The Gauteng Department of Social Development held a youth dialogue at Jameson Park in the Lesedi Municipality to discuss with young people various issues that affect them in their area. The dialogue focused on issues such as unemployment, teenage pregnancy, health issues and entrepreneurship opportunities available to the youth.

## Slide 66: Financial Report
PART C
Financial Performance
66

## Slide 67: DEPARTMENTAL EXPENDITURE AS AT 31 MARCH 2021: PER PROGRAMME
PROGRAMME | FINAL APPROPRIATION R’000 | EXPENDITURE R’000 | AVAILABLE R’000 | % SPENT
ADMINISTRATION | 719 624 | 681 065 | 38 559 | 95%
SOCIAL WELFARE SERVICES | 949 486 | 931 593 | 17 893 | 98%
CHILDREN AND FAMILIES | 2 582 864 | 2 278 267 | 304 597 | 88%
RESTORATIVE SERVICES | 741 530 | 728 341 | 13 189 | 98%
DEVELOP & RESEARCH | 893 845 | 830 025 | 63 820 | 93%
GRAND TOTAL | 5 887 349 | 5 449 291 | 438 058 | 93%

## Slide 68: REASONS FOR DEVIATION - SUMMARY PER PROGRAMME
It is expected that the % spent at the end of March reporting should be at 100% and the overall percentage spent as at 31 March 2021 is 93%.
Programme 1: Administration - 95%
The programme underspent the allocated budget due to delays experienced in the filling of vacant posts.
Funds allocated for investigations, the appointment of probity auditors, training, legal services, and fleet services were not spent in full by the end of the financial year.
Programme 2 : Social Welfare Services - 98%
The underspending in this programme was affected by unspent funds on ART food parcels and the allocated budget for HIV social behaviour change not spent in full at the end of the financial year.
Underspending was also reported on buildings and other fixed structures, as the allocation for the upgrading and rehabilitation of institutions were not not spent in full.

## Slide 69: REASONS FOR DEVIATION - SUMMARY PER PROGRAMME
Programme 3: Children and Families - 88%
The programme underspending was affected by additional budget received in the third quarter for a Presidential ECD Employment Stimulus Relief Fund that was not spent.
The verification process for qualifying NPOs was only finalised late in the financial year.
The school uniform budget was also not fully spent due to delays in the manufacturing process after the appointed co-operatives failed to deliver on time.
An underspending on buildings and other fixed structures following disputes between the contractors and implementing agents based on submitted compensation events (variation orders).

## Slide 70: REASONS FOR DEVIATION - SUMMARY PER PROGRAMME
Programme 4: Restorative Services - 98%
The underspending in this programme is due to delays in the implementation of substance abuse-related mobile services because of lockdown restrictions.
The Department contracted with NPOs from the third quarter onwards, after the easing of lockdown regulations.
Programme 5: Development and Research- 93%
The budget for food relief, dignity packs, and research affected the under expenditure in this programme.
In terms of food relief, some of the service providers submitted invoices after the cut-off date for the payment run in the province at the end of the financial year.
The expenditure for the programme was also affected by underspending of the allocated budget for NPOs.

## Slide 71: DEPARTMENTAL EXPENDITURE AS AT 31 MARCH 2021: ECONOMIC CLASSIFICATION
STD ITEM | FINAL APPROPRIATION | EXPENDITURE | AVAILABLE | % SPENT
COMPENSATION OF EMPLOYEES | 1 863 866 | 1 769 894 | 93 972 | 95%
GOODS AND SERVICES | 1 313 936 | 1 133 414 | 180 522 | 86%
DEPART AGENCIES AND ACCOUNTS | 64 | 64 | - | 100%
NON-PROFIT INSTITUTIONS | 2 571 152 | 2 433 038 | 138 114 | 95%
HOUSEHOLDS | 9 581 | 9 581 | - | 100%
BUILD AND OTHER FIXED STRUCTURES | 74 545 | 54 700 | 19 845 | 73%
MACHINERY AND EQUIPMENT | 53 909 | 48 345 | 5 564 | 90%
SOFTWARE AND OTHER INTAN ASSETS | 158 | 117 | 41 | 73%
PAYMENTS FOR FINANCIAL ASSETS | 138 | 138 |  | 101%
GRANT TOTAL | 5 887 349 | 5 449 291 | 438 058 | 93%

## Slide 72: REASONS FOR DEVIATION - SUMMARY PER ECONOMIC CLASSIFICATION
Compensation of employees - 95%
The under-expenditure on compensation of employees is due to delays in filling vacant posts and accelerated grade progression not paid in March as anticipated.
Goods and Services - 86%
The underspending on goods and services was mainly affected by the unspent funds destined for ART food parcels.
The school uniform budget was not fully spent either due to the start of the manufacturing process by the appointed service providers being delayed by the COVID-19 restrictions and schools having been closed until late in the financial year.
The food relief budget was not spent in full as there were outstanding invoices at the end of the financial year.
Spending on advertising, consultant and research projects, bursaries, legal services, fleet services, and training and development was negatively affected by the lockdown regulations.

## Slide 73: REASONS FOR DEVIATION - SUMMARY PER ECONOMIC CLASSIFICATION
Non-Profit Institutions - 95%
Underspending on NPOs is due to an additional budget of R77 763 000 received in the third quarter for the Presidential ECD Employment Stimulus that was not spent by the end of the financial year.
The ECD budget (both conditional grants and equitable shares) was under-spent due to the reduced number of beneficiaries in centres.
Buildings & Other Fixed Structures - 73%
Underspending in this category emanated from a dispute between contractors and implementing agents arising from a submitted compensation event (variation order).

## Slide 74: REASONS FOR DEVIATION - SUMMARY PER ECONOMIC CLASSIFICATION
Machinery & Equipment – 90%
The allocation for machinery and equipment was not spent in full due to delays being experienced in the delivery of some office furniture and equipment.
Software & Int Assets - 73%
The budget allocated for purchasing software had not been spent in full by the end of the financial year as anticipated.

## Slide 75: CONDITIONAL GRANT AS AT 31 MARCH 2021
NAME OF THE GRANT | FINAL APPROPRIATION R’000 | EXPENDITURE R’000 | AVAILABLE R’000 | % SPENT
ECD ADMINISTRATION | 4 140 | - | 4 140 | 0%
ECD CENTRE MAINTENANCE | 3 442 | 792 | 2 650 | 23%
ECD SUBSIDY EXPANSION | 127 647 | 115 497 | 12 150 | 90%
PEI:EARLY CHILDHOOD DEV GRANT | 77 763 | - | 77 763 | 0%
EPWP INCEN GRNT FOR PROV | 21 157 | 21 157 |  | 100%
GRAND TOTAL | 234 149 | 137 446 | 96 703 | 59%

## Slide 76: REASONS FOR DEVIATION - CONDITIONAL GRANTS
ECD (ADMINSTRATION) - 0%
Contract workers to monitor the ECD conditional grant were not spent by end of the financial year.
ECD (CENTRE MAINTENANCE) - 23%
The budget allocated to procure PPE’s for ECD Centers was not spent in full by the end of the financial year.
ECD (SUBSIDY EXPANSION) - 90%
Underspending on subsidy component of the ECD conditional grant budget was affected by the reduced number of beneficiaries in some centres and the change in the by laws by Tshwane municipalities.
PEI:EARLY CHILDHOOD DEV GRANT - 0%
Additional budget of R 77.7 million received in the third quarter for Presidential ECD Employment Stimulus Relief Fund not spent as the verification process for qualifying NPOs was finalised late in the financial year.

## Slide 77: PAYMENT OF INVOICES WITHIN 15 DAYS
MONTH | TOTAL NUMBER OF INVOICES RECEIVED | NO OF INVOICES PAID WITHIN 15 DAYS | NO OF INVOICES PAID BEYOND 15 DAYS | % OF INVOCIES PAID WITHIN 15 DAYS | REASONS FOR DEVIATIONS
April | 1 566 | 1 515 | 51 | 97% | There was a delay in confirmation of goods received by end-user as a result of online submission. Vendor profiles were also blocked due to expired Tax Clearance Certificate Bank account validation error that VMD delayed to rectify.
May | 1 829 | 1 632 | 197 | 89% | 
June | 684 | 618 | 66 | 90% | 
July | 1 839 | 1 485 | 354 | 81% | 
August | 2 217 | 2 102 | 115 | 95% | 
September | 1 31 | 983 | 48 | 95% | 
October | 3 553 | 2 994 | 559 | 84% | 
November | 1 407 | 1 132 | 275 | 80% | 
December | 1 064 | 938 | 126 | 88% | 
January | 3 405 | 2 857 | 548 | 84% | 
February | 1 350 | 1 103 | 247 | 82% | 
March | 1 776 | 1 508 | 268 | 85% | 
TOTAL | 20 690 | 18 867 | 2 854 | 91% | 

## Slide 78: PAYMENT OF INVOICES WITHIN 30 DAYS
MONTH | TOTAL NUMBER OF INVOICES RECEIVED | NO OF INVOICES PAID WITHIN 30 DAYS | NO OF INVOICES PAID BEYOND 30 DAYS | % OF INVOICES PAID WITHIN 30 DAYS | REASONS FOR DEVIATIONS
April | 1 566 | 1 549 | 17 | 99% | There was a delay in confirmation of goods received by end-user as a result of online submission. Vendor profiles were also blocked due to expired Tax Clearance Certificate Bank account validation error that VMD delayed to rectify.
May | 1 829 | 1 790 | 39 | 98% | 
June | 684 | 39 | 645 | 94% | 
July | 1 839 | 1 772 | 67 | 96% | 
August | 2 217 | 2 180 | 37 | 98% | 
September | 1 031 | 1 019 | 12 | 99% | 
October | 3 553 | 3 448 | 105 | 97% | 
November | 1 407 | 1 394 | 13 | 99% | 
December | 1 064 | 1 050 | 14 | 99% | 
January | 3 405 | 3 289 | 116 | 97% | 
February | 1 350 | 1 323 | 27 | 98% | 
March | 1 776 | 1 695 | 81 | 95% | 
TOTAL | 21 721 | 20 548 | 1 173 | 95% | 

## Slide 79: PREFERENTIAL PROCUREMENT SPENT AS AT 31 MARCH 2021
HDI (BBBEE) CATEGORY | FOURTH QUARTER TARGET 2020/21 FY | ACTUAL ACHIEVEMENT AS AT 31 MARCH 2021 | NUMBER OF COMPANIES | TOTAL SPENT
HDI | BBBEE Contribution : 80% | BBBEE :85.66% | 1 296 | R628 928 473,53
Women | Women : 30% | Women :45.72% | 653 | R141 923 447,72
Youth | Youth : 10% | Youth :16.71% | 589 | R134 169 674,86
PWD | PWD : 5% | PWD :42,62% | 126 | R18 368 776,87

## Slide 80: TOWNSHIP ECONOMY REVITILISATION SPENT AS AT 31 MARCH 2021
DEPARTMENT NAME | TOWNSHIP SPEND | NON TOWNSHIP | Unclassified | TOTAL GPG SPEND | % TOWNSHIP
Vote 6: Social Development | R278 062 790,38 | R288 569 912,09 | R257 804 151,43 | R824 437 853,78 | 36.55%
PROGRESS ON IMPLEMENTATION OF TOWNSHIP ECONOMIC REVITALISATION STRATEGY
Provincial annual target : 40.00%
Achievement as at 28 February 2021 : 36.55%

## Slide 81: Recommendation
It is recommended that the Portfolio Committee note the 2020/21 FY report as presented.
81