## Slide 1: Department of Roads and Transport
Portfolio Committee
June 2022

## Slide 2: Purpose
To apprise the Portfolio Committee of the progress of the Route Determination for the proposed Gauteng Rapid Rail Integrated Network Extensions Project

## Slide 3: Gauteng Rapid Rail Integrated Network (GRRIN) Extensions Project
Feasibility Study for Possible Rail Extensions to the Gauteng Network
  The premise of the GRRIN Extensions Project is the ITMP25 (August 2013)
  Extensive feasibility study for possible extensions the existing rapid rail network undertaken by the GMA (November 2016)
  TA1 application for Phase 1 submitted to National Treasury (April 2017)

## Slide 4: Gauteng Rapid Rail Integrated Network (GRRIN) Extensions Project
Proposed GRRIN Extensions

## Slide 5: Route Determination Process
Legislative requirement as per Section 6 of the GTIA and enables the following
  The first step in the process of defining the future railway reserve
  Determines a 400m-wide land corridor in which the future railway reserve may be located
  Enables the MEC to have rights over any land-use changes within this corridor
  Prevents land speculation over the location of the future rail reserve
  Provides a basis for Preliminary Design which aims to define the cadastral boundaries of the railway line, enables proclamation, expropriation, and procurement scope

## Slide 6: Route Determination Process
Route Determination Process as per Section 6 of the GTIA

## Slide 7: Route Determination for the GRRIN Extensions
Route Determination Programme

## Slide 8: Route Determination for the GRRIN Extensions
Route Determination for Phase 1 of the GRRIN Extensions
  Preliminary Route Alignment Study Initiated by MEC (October 2018)
  Route Alignment Options (July 2019)
  Environmental Investigation of Route Alignment Options (November 2019)
  Stakeholder Consultation (August 2019-June 2021)
  Public Participation (July 2021-August 2021)
  Recommended Route (December 2021)
  GPG EXCO of Determination of the Route (March 2022)
  Publication of the Determined Route (May 2022)

## Slide 9: Route Determination for the GRRIN Extensions
Route Determination for Phase 1 of the GRRIN Extensions

## Slide 10: Route Determination for the GRRIN Extensions
Route Alignment Options for Phase 1 of the GRRIN Extensions

## Slide 11: Route Determination for the GRRIN Extensions
Recommended Route for Phase 1 of the GRRIN Extensions

## Slide 12: Route Determination for the GRRIN Extensions
High-Level Risks for Route Determination

## Slide 13: Route Determination for the GRRIN Extensions
Conclusions & Recommendations for Route Determination for Phase 1
  Legislative requirements of GTIA fully complied to
  Recommended route is the best possible alignment in regard to:
    Environmental Impact
    Total Cost of System
    Land Affected
    Social Impact
    Economic Impact
    Station Locations
    Further Connection to Soweto through Roodeport

## Slide 14: Route Determination for the GRRIN Extensions
Conclusions & Recommendations for Route Determination for Phase 1
  Independent Technical Paper on the Economic and Financial Impact of the GRRIN Concludes:
    Rail networks are still essential for cities providing critical urban mobility and serve as key catalysts for equitable and sustainable economic recovery
    It is critical that rail networks remain at the core of their cities’ transport systems supported by flexible modes like buses or BRT, congestion mitigating measures, and land use and development policies – Alignment to ITMP25
    Determination of the future route continues in lieu of growing passenger demand to safeguard space as early as possible (as is the practice with roads master planning)

## Slide 15: Route Determination for the GRRIN Extensions
Route Determination 2: Soweto Extension & Cosmo City Junction
  The process to determine the route for the Soweto Extension and Cosmo City Junction has been initiated by the GMA
  Includes Prefeasibility Study on further Extensions to the GRRIN
  The project through which this process will be undertaken is in procurement
Route Determination 3: Mamelodi & Boksburg Extensions
  Initiation of the process to determine the route for the Mamelodi and Boksburg extension is planned for the 2024/25 FY

## Slide 16: Route Determination
The End