## Slide 1: GAUTENG DEPARTMENT OF SOCIAL DEVELOPMENT
2023/2024 2nd QUARTER PERFORMANCE MONITORING REPORT
ANALYSIS OF PERFORMANCE
  SOCIAL DEVELOPMENT PORTFOLIO COMMITTEE
  2023

## Slide 2: Table Of Contents
  Part A: Overview Of Department Performance.
  Part B: Non-financial Performance
  1. Programme Performance
  2. Governance And Administration
  3. Areas of Significant Deviation from Planned Performance
  4. Monitoring of NPOs
  5. Extraordinary Issues
  Part C: Financial Report

## Slide 3: Purpose
To present departmental performance for the 2nd Quarter of 2023/24 FY.

## Slide 4: Table Of Contents
PART A
Non-financial performance report Technical analysis per programme/sub-programme

## Slide 5: Rating Categories
The performance for the Department is disaggregated according to the threshold represented by the following ratings categories and definitions:
Rating Symbol | Rating Category | Value
 | Achieved | 100% and greater
 | Not Achieved: Good progress | 76% - 99%
 | Not Achieved: Fair progress | 51% - 75%
 | Not Achieved: Poor Progress | 26% - 50%
 | Not Achieved: Very Poor Progress | Less than 26%
 | Not targeted for the Q | No quarterly targets set for the quarter under review.

## Slide 6: Legend

## Slide 7: Overview of Q2 Non-Financial Performance
Chart: Departmental Overview
| PROG 1: ADMINISTRATION | PROG 2: SOCIAL WELFARE SERVICES | PROG 3: CHILDREN & FAMILIES | PROG 4: RESTORATIVE SERVICES | PROG5: DEVELOPMENT & RESEARCH | OVERALL DEPT PERFORMANCE
Achieved (100% and greater) | 0.4 | 0 | 0.83333 | 0.82353 | 0.64 | 0.60274
Good Progress (greater than 75% | 0.1 | 0.55556 | 0 | 0.11765 | 0.12 | 0.15068
Fair Progress (51% - 75%) | 0.1 | 0.22222 | 0.16667 | 0.058824 | 0.08 | 0.10959
Poor Progress (26% - 50%) | 0.1 | 0.11111 | 0 | 0 | 0 | 0.027397
Very Poor Progress (Less than 25%) | 0 | 0.11111 | 0 | 0 | 0.12 | 0.054795
Not Targeted | 0.3 | 0 | 0 | 0 | 0.04 | 0.054795
Annual YTD | 0.4 | 0 | 0.41667 | 0.35294 | 0.04 | 0.21918
IYTD Achieved | 0.625 | 0 | 0.75 | 0.94118 | 0.64 | 0.64789

## Slide 8: Q2 Overall Department Overview
Chart: Departmental Overview
| Quarterly Achievement | Interim Year To Date | Year To Date
Q1 | 0.61 | 0.61 | 0.14
Q2 | 0.64 | 0.65 | 0.22

## Slide 9: Quarterly Year On Year Comparison
Chart: Year on Year Comparison
| Prog 1: Administration | Prog 2: Social Welfare Services | Prog 3: Children and Families | Prog 4: Restorative Services | Prog 5: Development and Research | Overall Performance
Q2: 22/23FY | 0.95 | 0.5 | 0.82 | 0.89 | 0.73 | 0.8
Q2: 23/24FY | 0.57 | 0 | 0.83 | 0.82 | 0.67 | 0.64

## Slide 10: Q2 Achievement vs Weighted Performance
Chart: Achievement vs Weighted Performance
| Quarterly Achievement | Quarterly Weighted rating scale
Q1 | 0.61 | 0.86
Q2 | 0.64 | 0.86

## Slide 11: Non-Financial Vs Financial Comparison: AYTD
Weighted YTD Non-Financial performance against YTD financial expenditure
Chart: Q2 YTD Non-financial vs. Financial performance
| Overall Dept perfomance | Prog1 | Prog 2 | Prog 3 | Prog 4 | Prog 5
Non Financial performance(%) | 0.66 | 0.66 | 0.71 | 0.78 | 0.74 | 0.53
Financial Expenditure(%) | 0.44 | 0.55 | 0.6 | 0.49 | 0.36 | 0.29

## Slide 12: Departmental Achievement of National and Provincial Strategic Priorities
STRATEGIC LINKAGES |  | STRATEGIC PLANNING | STRATEGIC REPORTING
NDP/MTSF Priority | GGT Priority | Outcome as per approved Dept Strat Plan | Summarised Dept Performance during Q2
Priority 2: Economic transformation and job creation | Priority 1: Economy, Jobs & Infrastructure | Reduce hunger and poverty | National Priority 2 Of the 14 planned targets, 5 were fully achieved at 35.71%; 1 target illustrated good progress representing 7.14%, 2 targets demonstrated fair progress representing 14.29%; 3 targets representing 21.43.1% showed poor progress, while 3 targets representing 21.43% were not targeted for during quarter under review. Provincial Priority 1 Of the 10 planned targets, the Department achieved 4 targets representing 40%; 1 target showed good progress representing 10%, 2 targets demonstrated fair progress representing 20% and 3 targets representing 30% showed poor progress ..
Priority 4: Consolidating the social wage through reliable and quality basic services. | Priority 4: Safety, Social Cohesion and Food Security | Enhanced care and protection of poor and vulnerable groups Reduce hunger and poverty Reduce the demand for substances and harm caused by substances | National Priority 4 Of the 18 planned targets, the Department achieved 10 targets representing 55,56% 3 targets showed good progress representing 16,67% , 2 targets showed fair progress representing 11,11%, 1 target representing 5,56% showed poor progress ,1 target representing 5,56% showed very poor progress while 1 target representing 5,56% was not targeted for during quarter under review. Provincial Priority 4 Of the 19 planned targets, the Department achieved 11 targets representing 57.89 %; 3 targets showed good progress representing 15.79%; 2 target demonstrated fair progress representing 10.53%; 1 target demonstrated poor progress representing 5,26% ,1 target demonstrated very poor progress representing 5,26% while 1 target representing 5,26% was not targeted for during quarter under review.

## Slide 13: Q2 Provincial Priorities
Chart: Achievement of Provincial Strategic Priorities
| Priority 1: Economy, Jobs & Infrastructure | Priority 4: Safety, Social Cohesion and Food Security
Achieved (100% and greater) | 0.4 | 0.57895
Good Progress (greater than 75%) | 0.1 | 0.15789
Fair Progress (51% - 75%) | 0.2 | 0.10526
Poor Progress (26% - 50%) | 0.3 | 0.052632
Very Poor Progress (Less than 25%) | 0 | 0.052632
Not Targeted | 0 | 0.052632

## Slide 14: Q2 National Priorities
Chart: Achievement of National Strategic Priorities
| Priority 2: Economic Transformation and Job Creation | Priority 4: Consolidating the social wage through reliable and quality basic services
Achieved (100% and greater) | 0.35714 | 0.55556
Good Progress (greater than 75%) | 0.071429 | 0.16667
Fair Progress (51% - 75%) | 0.14286 | 0.11111
Poor Progress (26% - 50%) | 0.21429 | 0.055556
Very Poor Progress (Less than 25%) | 0 | 0.055556
Not Targeted | 0.21429 | 0.055556

## Slide 15: Table Of Contents
Part B:
Non-financial Performance
1. Programme Performance

## Slide 16: Overview Of Q2 Non-Financial Performance: Prog 2
Chart: Programme 2: Social Welfare Services
| 2.2 Services to Older Persons | 2.3 Services to the Persons with Disabilities | 2.4 HIV and AIDS
Achieved (100% and greater) | 0 | 0 | 0
Good Progress (greater than 75% | 0.5 | 1 | 0.4
Fair Progress (51% - 75%) | 0.5 | 0 | 0.2
Poor Progress (26% - 50%) | 0 | 0 | 0.2
Very Poor Progress (Less than 25%) | 0 | 0 | 0.2
Not Targeted | 0 | 0 | 0

## Slide 17: Care and Service to Older Persons
During the quarter under review :
13 963 (T:19 675) older persons were reached through services provided by funded community-based care and support facilities (home based; service centres and luncheon clubs) and
5 740 (T:6 146) older persons benefitted from residential facilities.

## Slide 18: Services to Persons with Disabilities
During the period under review the following were achieved:
Residential care were accessed by 1 667 (T:1 703) Persons with Disabilities in government and NPO managed facilities;
Protective workshop programme aimed at socio-economic empowerment of persons with disabilities reached 3 670 (T:4 265) beneficiaries.

## Slide 19: HIV And AIDS & EPWP
During the period under review the following were achieved:
Nutritional support was provided to 69 803(T:74 100) through food parcels to date and 10 732 (T:32 300) through cooked meals
82 120 (T:108 865) beneficiaries received psychosocial support services including Orphans and Vulnerable Children
5 543 (T:7 432) work opportunities were created through EPWP
Care and Support Programme
Comprehensive core package of services that include nutritional support, counseling, skills development, home and school visits, psychosocial support, educational support, access to treatment, and referrals was provided to:
Orphans, Vulnerable Children and Youth (OVCY)
Youth Headed Households
Children Living with HIV
Adults on ARVs supported
Beneficiaries with TB / showing signs thereof
Older Persons, who are primary Caregivers

## Slide 20: Overview Of Q2 Non-Financial Performance: Prog 3
Chart: Programme 3: Children and Families
| 3.2 Care and Services to Families | 3.3 Child Care and Protection | 3.4 Child and Youth Care Centres | 3.5 Community-Based Care Services for children
Achieved (100% and greater) | 1 | 0.75 | 1 | 0
Good Progress (greater than 75% | 0 | 0 | 0 | 0
Fair Progress (51% - 75%) | 0 | 0.25 | 0 | 1
Poor Progress (26% - 50%) | 0 | 0 | 0 | 0
Very Poor Progress (Less than 25%) | 0 | 0 | 0 | 0
Not Targeted | 0 | 0 | 0 | 0

## Slide 21: Care And Support To Families
During the quarter under review the following was achieved:
  225 541 (T:35 658) family members participated in preservation programmes
  647 (T:523) family members were reunited with their families
  26 702 (T:22 710) family members participated in parenting programmes
  2 603 (T:2 400) homeless persons were admitted into homeless shelters

## Slide 22: Child Care And Protection
During the period under review:
920 (T:1 629) children in need of care and protection were placed in foster care.
1 047 (T:384) children were reported as cases of child abuse.
3 780 (T:4 423) children were placed in CYCCs for developmental social welfare services.

## Slide 23: Overview Of Q2 Non-Financial Performance: Prog 4
Chart: Programme 4: Restorative Services
| 4.2 Crime Prevention and support | 4.3 Victim empowerment | 4.4 Substance Abuse, Prevention and Rehab
Achieved (100% and greater) | 0.66667 | 0.875 | 0.83333
Good Progress (greater than 75% | 0 | 0.125 | 0.16667
Fair Progress (51% - 75%) | 0.33333 | 0 | 0
Poor Progress (26% - 50%) | 0 | 0 | 0
Very Poor Progress (Less than 25%) | 0 | 0 | 0
Not Targeted | 0 | 0 | 0

## Slide 24: Crime Prevention and Support
During the period under review the following were achieved:
Social crime prevention and awareness campaigns reached 835 667 (T:1 199 643) children and adults.
All children and adults in conflict with the law referred to the Department for further interventions were attended to:
  1 196 (T:643) completed diversion programmes.
  Secure care centers accommodated 423 (T:360) children in conflict with the law.
Capacity building
Post arrest training for probation officers was conducted on 3-5 July 2023 and 38 officials were reached.
Developmental assessment training was conducted on 10-14 July 2023 and 40 officials were reached.
Wake-up Call substance abuse program training was conducted on 22-24 August 2023
Probation Case Management (PCM) training on 28-31 October 2023 and 156 officials were reached.

## Slide 25: Victim Empowerment
During the period under review the following were achieved:
The Department continues to create awareness against gender-based violence (GBV); on the 25th of each month awareness is created around Orange Day.
The Department has a Gender Based Violence unit that provides psycho-social counselling to adult victims of violence. This unit creates awareness based on the National Strategic Plan on Gender-Based Violence and Femicide 2020-2030.
The Department funded 105 (T:108) facilities and shelters that provided psycho-social support to 28 203 (T:29 046) victims of violence and crime.
The programme of no violence against women and children including 16 days of activism reached 1 444 123 (T:974 854) beneficiaries.

## Slide 26: Substance Abuse Prevention and Rehabilitation
During the period under review
The Department continued to render substance abuse prevention and rehabilitation services in terms of the Prevention of and Treatment of Drug Dependency Act 70 of 2008 and the National Drug Master Plan to ensure that the demand and the harm caused by drugs is reduced.
2 570 238 (T:2 207 148) beneficiaries were reached through substance abuse prevention programmes.
The Ke-Moja coaches deployed in schools and communities to roll out the Ke-Moja Drug Prevention programme reached 842 889 (T: 686 867) children and youth as well as parents and caregivers; to date.
Substance abuse disorder treatment services were provided to 21 025 (T:126 564) users.
  4 511 (T:7 275) beneficiaries that completed treatment programmes are participating in after care programmes.

## Slide 27: Substance Abuse Prevention and Rehabilitation
During the period under review
  Registrations:
  The following facilities were registered in terms of the provisions of Act 70 of 2008:
  Thandanani Drop inn centre was registered as a community-based service on 24 July 2023.
  Nhlosenhle Drug and Substance Abuse Treatment Agency was re-registered as a community-based service on 10 August 2023.
Capacity building and training:
  Capacity building workshop on Harm reduction – the workshop focused on mental health and substance abuse. 61 stakeholders and Social Workers were in attendance.
  Participated in the HR induction programme on 25 July and presented on the elevated provincial substance abuse programme.

## Slide 28: Overview Of Q2 Non-Financial Performance: Prog 5
Chart: Programme 5: Development and Research
| 5.2 Community Mobilisation | 5.3 Institutional capacity building and support for NPOs | 5.4 Poverty Alleviation and Sustainable Livelihoods | 5.5 Community Based Research and Planning | 5.6 Youth development | 5.7 Women development | 5.8 Population Policy Promotion
Achieved (100% and greater) | 1 | 1 | 0.41667 | 1 | 0.5 | 1 | 0.8
Good Progress (greater than 75% | 0 | 0 | 0.16667 | 0 | 0.5 | 0 | 0
Fair Progress (51% - 75%) | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0
Poor Progress (26% - 50%) | 0 | 0 | 0 | 0 | 0 | 0 | 0
Very Poor Progress (Less than 25%) | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0.2
Not Targeted | 0 | 0 | 0.083333 | 0 | 0 | 0 | 0

## Slide 29: Poverty Alleviation And Sustainable Livelihoods
The Department through its funded organisations has:
  Poverty reduction programmes were accessed by 283 969 (T:1 242 426) beneficiaries.
  Distributed 22 054 (T:888 000) dignity packs for the year to date.
  Enabled the participation of 37 756 (T:32 376) people in income generation programmes.
  Distributed 103 234 (T:187 750) food parcels through foodbanks and 31 663 (T:22 500) persons received food through feeding programmes; to date.
  29 690 (T:36 553) beneficiaries participated in skills development programmes including youth
  14 270 (T:12 832) beneficiaries participated in the Welfare to work programmes; to date.
  78 (T:60) cooperatives provide goods and services to the Department.
  245 738 (T:27 015) youth participated in the youth mobilisation programmes

## Slide 30: Women Development
During the period under review the following were achieved:
The Department has established partnerships with various training institutions, development agencies, the private sector and other government agencies to train women in skills such as financial management, marketing, business development and procurement procedures.
18 826 (T:11 114) women participated in empowerment programmes; to date.
1 790 (T:1 358) women on child support grant were linked to economic opportunities.

## Slide 31: Departmental Infrastructure/ Capital Projects
DEPARTMENT INFRASTRUCTURE / CAPITAL PROJECTS |  |  |  |  |  | 
Name of Project | Brief description of project | Start Date | End Date | Current Status | Challenges | Requests for Intervention
Bantubonke Early Childhood Centre | Construction of Early Childhood Centre | 31 August 2017 | 29 March 2024 | On-hold | The slow progress has contractually translated into default on the side of the contractor which the contractor has failed to remedy. This unfortunately has resulted in the termination of the services of the Contractor. | Sourcing of a completion contractor is in a process of being finalized. The process of finalizing the Specifications and the works guarantee took longer than anticipated and the process to be completed in the subsequent quarters of 2024/25.
Bekkersdal Social Integrated Facility | Construction of Early Childhood, Community Facility for Older Persons, and Regional Offices | 31 July 2017 | 31 October 2024 | On-Hold | Professional Service providers poor performance as required per contract entered. Project on-hold pending contractual agreement to complete the works from both Professional Service Provider and the Contractor. | Intensification of stakeholder engagements and appointment of a suitable professional service provider to completion of the project.

## Slide 32: Departmental Infrastructure/ Capital Projects
DEPARTMENT INFRASTRUCTURE / CAPITAL PROJECTS |  |  |  |  |  | 
Name of Project | Brief description of project | Start Date | End Date | Current Status | Challenges | Requests for Intervention
Devon Early Childhood Centre | Construction of Early Childhood Centre | 30 April 2018 | 24 March 2021 | Completed | N/A | N/A
Ratanda Shelter | Construction of Shelter of Vulnerable | 31 July 2017 | Not yet available | Planning | N/A | N/A
Sebokeng Inpatient Rehab Centre | Construction of Inpatient Rehabilitation Centre | 31 July 2017 | Not yet available | Planning | N/A | N/A
Pretoria West Townlands (Soshanguve) Inpatient Rehab Centre | Construction of Inpatient Rehabilitation Centre | 01 October 2018 | Not yet available | Planning | N/A | N/A

## Slide 33: Departmental Infrastructure/ Capital Projects
DEPARTMENT INFRASTRUCTURE / CAPITAL PROJECTS |  |  |  |  |  | 
Name of Project | Brief description of project | Start Date | End Date | Current Status | Challenges | Requests for Intervention
Tembisa Inpatient Rehab Centre | Construction of Inpatient Rehabilitation Centre | 01 April 2018 | Not yet available | Planning | N/A | N/A
Walter Sisulu CYCC (Demolition and Reconstruction) | Demolition of Office Accommodation and Construction of new office accommodation | 31 July 2016 | Not yet available | Planning | N/A | N/A
Khutsong Social Integrated Facility | Construction of Early Childhood, Community Facility for Older Persons, and Regional Offices | 31 July 2017 | Not yet available | Planning | N/A | N/A
Foschville | Regional Office | 1 July 2022 | Not yet available | Planning | N/A | N/A

## Slide 34: Human Resource Capacity
Human Resource Capacity |  |  |  | 
During the period under review 01 July to 30 September 2023 |  |  |  | 
Total number of posts on the Dept. Structure as at the last day of the period under review | Total number of posts currently filled as at the last day of the period under review |  | Total number of vacant posts as at the last day of period under review | 
5 564 | 5 118 |  | 446 | 
Total number of acting positions as at the last day of the period under review | Total number of terminations during the period under review |  | Total number of new appointments during the period under review | 
5 | 41 |  | 28 | 
Total number of suspensions during the period under review | Summarized information on the GEYODI / HDI compliance for the period under review |  |  | 
Three employees was placed on precautionary suspension for the period under review. | Females: 75% (3 824 out of 5 118) | Youth: : 35% (1 775 out of 5 118) | Persons with disabilities: 5% (232 out of 5 118) | 
 | Race |  |  | 
 | African | Coloured | Indian | White
 | 96% (4 907 out of 5 118) | 2% (113 out of 5 118) | 0% (17 out of 5 118) | 2% (81 out of 5 118)

## Slide 35: Table Of Contents
Part B:
Non-financial Performance
2. Governance/ Administration

## Slide 36: Resolution Management
RESOLUTION MANAGEMENT |  |  |  |  | 
Reference Number | Date Received | Due Date | Detail / Title of Resolution | Progress to Date / Current Status | Date submitted to GPL
No reference | 30 September 2023 | 30 October 2023 | Focus intervention study report on the review of the state of victim friendly rooms and its effective role in dealing with gender-based violence. | Still in progress. | The report is due on 31 October 2023.
No reference | 29 May 2023 | 30 June 2023 | Adopted Social Development Committee Oversight Report on the Budget Vote 6 Report of the Department of Social Development for the 2023/24 financial year. | Submitted | Responses submitted 17 August 2023
SDQ4OR001 | 15 June 2023 | 31 July 2023 | Portfolio Committee on Social Development Oversight Report on the fourth Quarterly Report of the Department of Social Development for the 2022/23 financial year. | Submitted | Responses submitted 17 August 2023
Total number of Resolutions received from GPL during this Quarter |  |  |  |  | 1
Total number of Resolutions responses due to GPL during this Quarter |  |  |  |  | 0
Total number of Resolutions responded to and submitted back to GPL during this Quarter |  |  |  |  | 2

## Slide 37: Petitions Management
PETITIONS MANAGEMENT |  |  |  |  | 
Reference Number | Date Received | Due Date | Detail / Title of Petition | Progress to Date / Current Status | Date submitted to GPL
PP30B/09/23/CS | 29 October 2023 | 15 October 2023 | Referral of Petition: Rampant Drug Sale & Corrupt SAPS, Ref: PP30B/09/23/CS | The Department only received the Petition on 29 October 2023, and its intervention on the matter will provide the report by 30 October 2023. | Report will be availed on the 30 October 2023.
Total number of Petitions received from GPL during this Quarter |  |  |  |  | 1
Total number of Petitions responses due to GPL during this Quarter |  |  |  |  | 1
Total number of Petitions responded to and submitted back to GPL during this Quarter |  |  |  |  | 0

## Slide 38: Auditor–General & PSC Requests
Auditor – General REQUESTS FOR INFORMATION RECEIVED DURING THE PERIOD UNDER REVIEW] |  | 
 | Total number of AGSA Requests for Information received from AGSA during this Quarter | 4
 | Total number of AGSA Requests for Information due during this Quarter | 4
 | Total number of AGSA Requests for Information responded to and submitted back to AGSA during this Quarter | 4
PSC REQUESTS FOR INFORMATION
Public Service Commission REQUESTS FOR INFORMATION RECEIVED DURING THE PERIOD UNDER REVIEW] |  | 
 | Total number of PSC Requests for Information received from the PSC during this Quarter | 1
 | Total number of PSC Requests for Information due during this Quarter | 0
 | Total number of PSC Requests for Information responded to and submitted back to the PSC during this Quarter | 0

## Slide 39: Departmental Achievement on Actual GEYODI Empowerment
GENDER |  |  |  |  |  |  | 
Indicator | Male | Female | Undisclosed | LGBTQIA+ | Youth | Persons with Disabilities | Total
HIV/AIDS programmes | 58 917(32%) | 123 184(68%) | 105(0%) | 0(0%) | 39 821(22%) | 1 776(1%) | 182 206
Victim empowerment Programme | 14 793(5%) | 14441(5%) | 112103(40%) | 138324(50%) | 14 332(5%) | 410(0%) | 279 661
Poverty Alleviation and Sustainable Livelihoods | 47 680(41%) | 67 652(59%) | 106(0%) | 0(0%) | 72 678(63%) | 1 103(1%) | 115 438
Women Development Programme | 0(0%) | 10 920(100%) | 0(0%) | 0(0%) | 9 293(85%) | 33(0%) | 10 920
16 Days of Activism | 80 650(9%) | 118 985(14%) | 681 416(77%) | 662(0%) | 86 506(10%) | 741(0%) | 881 713
Grand Total | 202 040(14%) | 335 182(23%) | 793 730(54%) | 138 986(9%) | 222 630(15%) | 4063(0%) | 1 469 938

## Slide 40: Departmental Achievement on Actual GEYODI Empowerment
YOUTH |  |  |  |  |  |  | 
Indicator | Male | Female | Undisclosed | LGBTQIA+ | Youth | Persons with Disabilities | Total
All beneficiaries in Child & Youth Care Centres | 1 578(48%) | 1 719(52%) | 1(0%) | 0(0%) | 159(5%) | 367(11%) | 3 298
Youth Development Programme | 15 540(6%) | 16 528(7%) | 209 584(87%) | 0(0%) | 241 652(100%) | 298(0%) | 241 652
Crime Prevention Programme | 67 347(8%) | 75 726(9%) | 693 361(83%) | 13(0%) | 29 360(4%) | 845(0%) | 836 447
Substance Abuse Prevention, Treatment & Rehabilitation | 350 374(16%) | 398 434(18%) | 1 423 014 (66%) | 0(0%) | 172 165(8%) | 46 436(2%) | 2 171 822
Grand Total | 434 839(13%) | 492 407(15%) | 2 325 960(71%) | 13(0%) | 443 336(14%) | 47 946(1%) | 325 3219

## Slide 41: Departmental Achievement on Actual GEYODI Empowerment
DISABLED |  |  |  |  |  |  | 
Indicator | Male | Female | Undisclosed | LGBTQIA+ | Youth | Persons with Disabilities | Total
Services to Persons with Disabilities | 10 636(1%) | 14 802(2%) | 895 491(97%) | 0(0%) | 9 324(1%) | 7 337(1%) | 920 929
SENIOR CITIZENS |  |  |  |  |  |  | 
Indicator | Male | Female | Undisclosed | LGBTQIA+ | Youth | Persons with Disabilities | Total
Services to Older Persons | 13 017(5%) | 26 970(11%) | 215 438(84%) | 0(0%) | 6 284(2%) | 3 233(1%) | 255 425

## Slide 42: Governance/ Administration
The Department experienced challenges in relation to the provision of dignity packs and school uniforms due to the roll-over incurred from the previous financial year, there were delays in the finalisation of tender processes. Department will fast-track Supply Chain Management ( SCM) processes in the 2nd quarter.
Non-compliance with funding requirements and the meeting of minimum norms and standards for different fields of service by some NPOs remains a challenge facing the Department. The Department is continuously supporting and capacitating the affected NPOs for them to comply with funding requirements.
Performance on foster care placements is due to inability to acquire relevant reports from Psychologist & Psychiatric services from DoH, NDSD, as well as relevant legal documents from prospective foster parents for submission to Courts as well as the Department's reliance on external dependences i.e., DOJ (Awaiting Court Dates), SAPS (Police Clearance) and takeover of cases from dysfunctional CPOs. The Department continuously monitor the foster care management plan, including engagements with the courts, SAPS and Designated Child Protection Organisations (DCPOs)
The micro-management project has been initiated to mitigate the deviations of Foster Care Programme, as it relates to management of court orders. The project is attended by Provincial and Regional Management involved in the programme. The aim is to mitigate the lapsing of court orders.

## Slide 43: Challenges
Challenge | Consequence | Recommendation
Performance on issuing valid foster care orders was affected by the Department's reliance on external dependences i.e. DOJ(Awaiting Court Dates), SAPS (Police Clearance) and takeover of cases from dysfunctional CPOs. | In addition, the Department's annual cleaning of the SASSA Database (SOCPEN) against GDSD cases has led to a reduction of Foster Care Cases. The reduction cases relates to Children turning 18, death, Child no longer in need of care of protection, ID not corresponding with names, duplicate cases. | It is to be noted that the 2024/2025 target setting exercise will be based on the updated reduced cleaned out Database (SASSA/GDSD) as baseline.
The number of inpatient treatment beds is not sufficient to meet the demand for inpatient treatment services. | There are long waiting lists and service users become despondent awaiting for the treatment process. | Service users are referred for quick absorption to outpatient and community-based services for psychosocial support services. Department further conduct pre-admission support groups to keep service users motivated.

## Slide 44: Requests for Intervention
REQUESTS FOR INTERVENTION |  | 
What area / subject does this relate to | What intervention is sought from the Legislature? | Why is this intervention sought?
None - There were no interventions requests for GPL from the Office of the HOD. These are usually addressed during Department’s appearance at the Portfolio Committee. | None | None

## Slide 45: Table Of Contents
Part B:
Non-financial Performance
3. Areas of significant deviation from planned performance

## Slide 46: Indicators Showing Performance Below 80%
Performance Indicator | Quarter 2 Target | Quarter 2 Actual | 2023/24 Target | 2023/24 Actual | Reason for Deviation | Mitigating measure | % Achieved | % Achieved Annual
Number of service users who accessed Substance Use Disorder (SUD) treatment services | 26 564 | 21 025 | 46 038 | 21 025 | Target: Not Achieved Performance is due to limited availability of bed capacity which is receiving departmental consideration, bed space at the state facility has been incrementally upscaled when the new registration certificate was issued | The Department is currently engaging with GDID and funded NPOs to increase the current treatment capacity. The Department will continue to monitor progress in this regard. | 79% | 46%

## Slide 47: Indicators Showing Performance Below 75%
Performance Indicator | Quarter 2 Target | Quarter 2 Actual | 2023/24 Target | 2023/24 Actual | Reason for Deviation | Mitigating measure | % Achieved | % Achieved Annual
Number of EPWP work opportunities created. | 7 432 | 5 543 | 7 432 | 5 543 | Target: Not Achieved Performance is due to fewer beneficiaries accessing EPWP work opportunities than anticipated. Moreover there are some NPOs that could not be funded as they did not meet the funding requirements. | The Department will continue to facilitate access to the programme and support NPOS to comply with funding requirements. | 75% | 75%
Number of older persons accessing community-based care and support services | 19 675 | 13 963 | 19 675 | 16 635 | Target: Not Achieved Performance is due to fewer beneficiaries accessing community based services than anticipated. Moreover there are some NPOs that could not be funded due to non compliance at the time when the request for proposal closed. | The Department will continue to facilitate access to the programme and support NPOS to comply with funding requirements. | 71% | 85%
Number of beneficiaries receiving Psychosocial Support Services | 108 865 | 82 120 | 108 885 | 82 120 | Target: Not Achieved Performance is due to fewer beneficiaries accessing community based services than anticipated. Moreover there are some NPOs that could not be funded due to non compliance at the time when the request for proposal closed. | The Department will continue to facilitate access to the programme and Regional officials have been capacitated to roll-out the programme. | 75% | 75%

## Slide 48: Indicators Showing Performance Below 75%
Performance Indicator | Quarter 2 Target | Quarter 2 Actual | 2023/24 Target | 2023/24 Actual | Reason for Deviation | Mitigating measure | % Achieved | % Achieved Annual
Number of children with valid foster care orders. | 46 896 | 33 049 | 46 896 | 33 049 | Target: Not Achieved Performance was affected by the Department's reliance on external dependences i.e. DOJ(Awaiting Court Dates), SAPS (Police Clearance) and take over of cases from dysfunctional CPOs. In addition the Department's annual cleaning of the SASSA Database (SOCPEN) against GDSD cases has led to a reduction of Foster Care Cases. The reduction cases relates to Children turning 18, death, Child no longer in need of care of protection, ID not corresponding with names, duplicate cases. | The Department will continuously monitor the foster care management plan, including engagements with the courts, SAPS and Designated Child Protection Organisations (DCPOs). In addtion 2024/2025 Target setting exercise will be based on the updated cleaned out Database (SASSA/GDSD) | 70% | 70%
Number of children reached through community-based prevention and early intervention programmes | 21 263 | 12 434 | 21 263 | 12 434 | Target: Not Achieved Performance is due to fewer beneficiaries accessing community based services than anticipated. Moreover there are some NPOs that could not be funded due to non compliance at the time when the request for proposal closed. | The Department will continue to facilitate access to the programme and support NPOs to comply with funding requirements. | 58% | 58%

## Slide 49: Indicators Showing Performance Below 75%
Performance Indicator | Quarter 2 Target | Quarter 2 Actual | 2023/24 Target | 2023/24 Actual | Reason for Deviation | Mitigating measure | % Achieved | % Achieved Annual
Number of persons reached through social crime prevention programmes | 1 199 643 | 835 667 | 2 483 571 | 1 234 969 | Target: Not Achieved Performance is due to fewer beneficiaries reached through social crime prevention programmes | The Department will continue to intensify access to the programme. | 70% | 50%
Number of food relief issued to people through food banks | 187 750 | 103 234 | 551 000 | 103 234 | Target: Not Achieved Performance is due to delays in SCM processes which are at the advance stage of procurement. | The Department will resolve SCM issues and fast track implementation. | 55% | 19%
Number of cooperatives trained | 365 | 238 | 365 | 238 | Target: Not Achieved Performance is due to fewer beneficiaries trained than anticipated. | The Department will continue to facilitate access to the programme | 65% | 65%

## Slide 50: Indicators Showing Performance Below 50%
Performance Indicator | Quarter 2 Target | Quarter 2 Actual | 2023/24 Target | 2023/24 Actual | Reason for Deviation | Mitigating measure | % Achieved | % Achieved Annual
Number of contracts awarded by the Department to HDI/SMME companies. | 13 | 6 | 49 | 10 | Target: Not achieved because of PWD Performance is due to the implementation of departmental procurement strategy and provincial TER strategy and the continuous partnership with Provincial Treasury to correct the classification of identified service providers which were incorrectly classified in the Central Supply Database (CSD).The performance for people with disabilities is due to minimal procurement of goods and services in the quarter under review. Comment: Performance is as at the end of May 2023 due to alignment of the system by Gauteng Provincial Treasury. | The Department will continue to monitor implementation of the departmental procurement strategy and Provincial TER strategy. End users to enhance monitoring of deliveries and payment of PWD owned companies. | 46.0% | 20%
Number of beneficiaries receiving daily meals at HCBC organisations | 32 300 | 10 732 | 32 300 | 10 732 | Target: Not Achieved Performance is due to fewer beneficiaries accessing community based services than anticipated. Moreover there are some NPOs that could not be funded due to non compliance at the time when the request for proposal closed. | The Department will continue to facilitate access to the programme and encourage NPOs to work towards compliance with funding requirements. | 33% | 33%

## Slide 51: Indicators Showing Performance Below 25%
Performance Indicator | Quarter 2 Target | Quarter 2 Actual | 2023/24 Target | 2023/24 Actual | Reason for Deviation | Mitigating measure | % Achieved | % Achieved Annual
Number of implementers trained on social and behaviour change programmes | 55 | 0 | 220 | 58 | Target: Not Achieved Performance was due to the fact that the initial Training that was convening in Microsoft Teams had to be reschedule due technical glitches and physical session has been facilitated after closing of the first quarter reporting timeline. | Performance of the completed training will be reported in the subsequent quarter. | 0% | 26%
Number of people benefitting from poverty reduction initiatives | 1 242 426 | 238 969 | 2 808 142 | 283 969 | Target: Not Achieved Performance is due to delays in SCM processes which are at the advance stage of procurement. Comment: On the basis of Probity audit outcomes, the tender has been cancelled due to technicalities on sub-contracting. | The Department will resolve SCM issues and fast track implementation. | 23% | 10%

## Slide 52: Indicators Showing Performance Below 25%
Performance Indicator | Quarter 2 Target | Quarter 2 Actual | 2023/24 Target | 2023/24 Actual | Reason for Deviation | Mitigating measure | % Achieved | % Achieved Annual
Number of dignity packs distributed | 888 000 | 22 054 | 1 776 000 | 22 054 | Target: Not Achieved Performance is due to delays in SCM processes which impacted on the implementation of dignity packs programme . Comment: On the basis of Probity audit outcomes, the tender has been cancelled due to technicalities on sub-contracting. | The Department will resolve SCM issues and fast track implementation. | 2% | 1%
Number of population capacity development sessions conducted | 1 | 0 | 4 | 1 | Target: Not Achieved Performance is due to non attendance of the envisaged in the scheduled capacity development session. | The performance will be realised in the third quarter as per re-schedule capacity development session | 0% | 25%

## Slide 53: Table Of Contents
Part B:
Non-financial Performance
4. Monitoring Of NPOs

## Slide 54: Monitoring Of NPOs
CAPACITY BUILDING:
The Department capacitated 407 (T:300) NPOs
MONITORING AND EVALUATION:
Substance abuse prevention and rehabilitation
  Onsite monitoring of the Ke Moja Programme at African Youth Development Fund.
  Site inspection with Gauteng Provincial Treasury to Dr Fabian and Florence Ribeiro Treatment Centre.
Crime Prevention
  Quality assurance assessment review was conducted at Elim Clinic on 7 July 2023
  Quality assurance assessment review was conducted at Angels of Glory organisation on 24 July 2023
  Case audit was conducted at Soshanguve secure care centre on 1-3 August 2023
  Developmental Quality Assurance(DQA) was conducted at Walter Sisulu secure care centre on 14-18 August 2023
  On-site assessment was conducted at Nigel DSD offices on 19 September 2023

## Slide 55: Table Of Contents
Part B:
Non-financial Performance
5. Extraordinary Issues

## Slide 56: Extraordinary Issues
There were no extraordinary issues detected during Q2 reporting period.

## Slide 57: Key Success Stories
Welfare to Work beneficiary, Refilwe Tsotetsi “Social Development Recognises Women For Positive Roles In Their Communities”. | 33-year-old Refilwe Tsotetsi is a beneficiary of the Gauteng Department of Social Development’s Welfare to Work Program. She is from Small Farms in Sedibeng, and did a beauty therapy course at the Beauty Hub Academy, at Oakdene Branch in 2021. The Beauty Hub Academy is an NPO funded by the Department of Social Development and offers a variety of courses, which amongst others, include hair, beauty, and nails. Tsotetsi first found out about the learnership opportunities provided by the Department through the Beauty Hub Academy from a family member, and she took it upon herself to obtain more information, resulting in her enrolling for the course. Tsotetsi specialises in lash installation and make-up artistry and she currently runs a makeup studio in Small Farms where she serves between +-7 clients per day. She was one of the 150 delegates who attended the MEC’s High Tea event, which took place at Avianto Hotel, Muldersdrift on the last day of August. The event sought to honour and empower women achievers in various sectors within the Department of Social Development and the Department of Agriculture, Rural Development and Environment as part of observing Women’s Month.
Baikagetse expands to private schools “The department has provided a big market to us in terms of awarding us contracts to manufacture school uniforms for children in need” | Baikagetse Development and Primary Cooperative Limited (BDPCL) is one of the cooperatives that produces school uniform for more than five schools in Gauteng, as part of the Bana Pele Programme where the Gauteng Provincial Government provides a basket of services to pupils such as free transportation, health daily nutrition and school uniform. Baikagetse is situated in Springs, Ekurhuleni, and the cooperative was formed ten years ago by Nomathemba Sibanda who is the Chairperson, Johanna Rangwato Kgawane, Susan Masoko Mashapa , Nomcebo Cidy, Ginindza and Sendulo Obvious Sibanda. According to Sibanda, in 2016 they were awarded a contract to manufacture 500 school uniforms by the Gauteng Department of Social Development”. Currently, they are doing good and they are contracted to supply uniform for seven schools of which two of those are private schools, and they have been able to create employment for three people. “The department has provided a big market to us in terms of awarding us contracts to manufacture school uniforms for children in need and we are grateful for the opportunity to be part of Bana Pele Project, which is supported by Gauteng Department of Social Development,” added Sibanda.

## Slide 58: Table Of Contents
PART C
Financial Performance
Financial Report

## Slide 59: DEPARTMENTAL EXPENDITURE AS AT 30 SEPTEMBER 2023: ECONOMIC CLASSIFICATION
STANDARD ITEM | FINAL APPROPRIATION R’000 | TOTAL EXPENDITURE R’000 | AVAILABLE R’000 | % SPENT
COMPENSATION OF EMPLOYEES | 2 077 178 | 1 072 880 | 973 276 | 52%
GOODS AND SERVICES | 960 264 | 403 955 | 701 910 | 37%
DEPARTMENTAL AGENCIES & ACCOUNTS | 55 | 55 | 28 | 67%
NON-PROFIT INSTITUTIONS (NPI) | 2 364 984 | 939 253 | 1 365 396 | 41%
HOUSEHOLDS (HH) | 10 115 | 6 919 | 563 | 92%
BUILDINGS & OTHER FIX STRUCT | 75 921 | 31 602 | 42 648 | 43%
MACHINERY AND EQUIPMENT | 46 559 | 10 978 | 1 343 | 89%
PAYMENTS FOR FINANCIAL ASSET | 370 | 138 | (138) | 
GRAND TOTAL | 5 537 037 | 2 465 780 | 3 085 026 | 44%

## Slide 60: FINANCIAL PERFORMANCE REPORT – QUARTER TWO
` | TOTAL BUDGET |  |  | 
PROGRAMME | ORIGINAL BUDGET | ACTUAL SPENDING | VARIANCE | % (SPENT)
ADMINISTRATION | 718 409 | 392 834 | 325 575 | 55%
SOCIAL WELFARE SERVICES | 692 604 | 413 055 | 279 549 | 60%
CHILDREN AND FAMILIES | 1 965 543 | 965 815 | 999 728 | 49%
RESTORATIVE SERVICES | 959 904 | 342 811 | 617 093 | 36%
DEVELOPMENT & RESEARCH | 1 214 346 | 351 265 | 863 081 | 29%
TOTAL | 5 550 806 | 2 465 780 | 3 085 026 | 44%
ECONOMIC CLASSIFICATION |  |  |  | 
CURRENT PAYMENTS | 3 152 021 | 1 476 835 | 1 675 186 | 47%
COMPENSATION OF EMPLOYEES | 2 046 156 | 1 072 880 | 973 276 | 52%
GOODS & SERVICES | 1 105 865 | 403 955 | 701 910 | 37%
TRANSFERS | 2 312 214 | 946 227 | 1 365 987 | 41%
CAPITAL PAYMENTS | 86 571 | 42 580 | 43 991 | 49%
PAYMENTS FOR FINANCIAL ASSETS | - | 138 | (138) | 
TOTAL | 5 550 806 | 2 465 780 | 3 085 026 | 44%

## Slide 61: DEPARTMENTAL EXPENDITURE AS AT 30 SEPTEMBER 2023: ECONOMIC CLASSIFICATION
Compensation of Employee - 52%
The overall expenditure on this category is affected by implementation of the cost-of-living salary adjustment from April 2023.
Goods and Services - 37%
The under spending on goods and services is affected by delays in finalisation of school uniform, food parcels and dignity packs tenders.
Progress on the above tenders is as follows:
  School uniform tender is finalised and awarded.
  Food parcels tender is recommended but under review.
  Dignity packs tender to be advertised in October 2023.
Percentage spent is also affected by cost driver items such as Microsoft license, training and bursaries which are scheduled to be paid in the third and fourth quarter of the financial year.

## Slide 62: DEPARTMENTAL EXPENDITURE AS AT 30 SEPTEMBER 2023: ECONOMIC CLASSIFICATION
Departmental Agencies and Accounts - 67%
TV license fees were fully paid and surplus amount will be redirected to areas of spending pressures.
Non- Profit Institutions - 41%
The underspending in this category is affected by the following:
Uncommitted funds due to non-complying NPOs.
NPOs that were earmarked for signing of agreements but could not sign due to bank account or name change or programme certificate or adverse monitoring outcome issues.
Households - 92%
Hight percentage spent is due to payment of leave gratuities and injury on duty claims processed since the beginning of the financial year.

## Slide 63: DEPARTMENTAL EXPENDITURE AS AT 30 SEPTEMBER 2023: ECONOMIC CLASSIFICATION
Building & Other Fixed Structure - 43%
The underspending in this category is affected by new construction of social infrastructures which is schedule to accelerate from third quarter of the financial year once all invoices and claims are received from implementing agents for the work completed.
Machinery & Equipment - 89%
High percentage spent is due to accruals for late delivery of assets from the previous financial year and procurement of assets for newly appointed and replacement of assets for officials at Head office, regions, and institutions.
Payments for financial asset
The department wrote off irrecoverable debts in August 2023. Funds will be reprioritised within the current budget to cater for the expenditure incurred.

## Slide 64: CONDITIONAL GRANT AS AT 30 SEPTEMBER 2023
64
NAME OF GRANT | BUDGET R’000 | EXPENDITURE R’000 | AVAILABLE R’000 | % SPENT
EPWP INTEGRATED GRANT FOR PROV | 22 444 | 11 213 | 11 231 | 50%
TOTAL | 22 444 | 11 213 | 11 231 | 50%
EPWP Incentive Grant - 50%
The overall expenditure is on track at this period of the financial year.

## Slide 65: 15- & 30-DAYS PAYMENT ANALYSIS
15 AND 30 DAYS PAYMENT ANALYSIS |  |  |  |  |  |  | 
Sundry payments | Total | Apr | May | June | July | Aug | Sep
Total Number of payments made | 770 | 31 | 199 | 97 | 143 | 177 | 123
Total number of payments within 15 days | 720 | 22 | 184 | 91 | 131 | 176 | 116
% payment within 15 days | 94% | 71% | 92% | 94% | 92 % | 99% | 94%
Total number of payments within 30 days | 769 | 31 | 199 | 96 | 143 | 177 | 123
% payment within 30 days | 99.87% | 100% | 100% | 99% | 100 % | 100% | 100%
Number of payments outside 30 days | 1 | 0 | 0 | 1 | 0 | 0 | 0
65
SAP Supplier payments | Total | Apr | May | June | July | Aug | Sep
Total Number of payments made | 3 977 | 373 | 620 | 798 | 732 | 822 | 632
Total number of payments within 15 days | 3 485 | 307 | 501 | 695 | 637 | 761 | 584
% payment within 15 days | 87.63% | 82% | 81% | 87% | 87% | 93% | 93%
Total number of payments within 30 days | 3 948 | 370 | 602 | 795 | 728 | 822 | 631
% payment within 30 days | 99.27% | 99% | 97% | 100% | 99% | 100% | 99.8%
Number of payments outside 30 days | 30 | 3 | 18 | 3 | 4 | 1 | 1

## Slide 66: 15 & 30 DAYS PAYMENT ANALYSIS (CONT..)
15 AND 30 DAYS PAYMENT ANALYSIS |  |  |  |  |  |  | 
NPI Payments | Total | Apr | May | June | July | Aug | Sep
Total Number of payments made | 3 171 | 368 | 995 | 189 | 1 512 | 92 | 15
Total number of payments within 15 days | 3 165 | 367 | 992 | 187 | 1 512 | 92 | 15
% payment within 15 days | 99.81% | 100% | 100% | 99% | 100% | 100% | 100%
Total number of payments within 30 days | 3 170 | 368 | 995 | 188 | 1 512 | 92 | 15
% payment within 30 days | 99.97% | 100% | 100 % | 99 % | 100% | 100% | 100
Number of payments outside 30 days | 1 | 0 | 0 | 1 | 0 | 0 | 0
66
OVERALL PERFORMANCE | Total | Apr | May | June | July | Aug | Sep
Total Number of payments made | 7 918 | 772 | 1 814 | 1 084 | 2 387 | 1091 | 770
Total number of payments within 15 days | 7 370 | 696 | 1 677 | 973 | 2280 | 1029 | 715
% payment within 15 days | 93.08% | 90% | 92% | 90% | 96% | 94% | 93%
Total number of payments within 30 days | 7 886 | 769 | 1 796 | 1 079 | 2 383 | 1090 | 769
% payment within 30 days | 99.60% | 100% | 99.% | 100% | 100% | 100% | 99.8
Number of payments outside 30 days | 32 | 3 | 18 | 5 | 4 | 1 | 1

## Slide 67: PREFERENTIAL PROCUREMENT SPEND : 01 JULY 2023 – 30 SEPTEMBER 2023
HDI (BBBEE) CATEGORY | SECOND QUARTER TARGET 2023/24 FY | ACTUAL ACHIEVEMENT 01 JULY –30 SEP 2023 | TOTAL SPENT
HDI | BBBEE Contribution : 80% | BBBEE : 89.01% | R152 878 049.91
Women | Women : 40% | Women: 45.67% | R78 515 176.29
Youth | Youth : 10% | Youth : 40.09% | R69 578 269.72
PWD | PWD : 5% | PWD : 3.72% | R6 534 049.46
67

## Slide 68: TOWNSHIP ECONOMY REVITILISATION SPEND : 01 JULY 2023 – 30 SEPTEMBER 2023
DEPARTMENT NAME | TOWNSHIP SPEND | NON-TOWNSHIP | Unclassified | TOTAL GPG SPEND | % TOWNSHIP SPEND
Vote 6: Social Development | R86 952 045.32 | R80 025 333.04 | R3 590 432.20 | R170 567 810.56 | 50.46%
PROGRESS ON IMPLEMENTATION OF TOWNSHIP ECONOMIC REVITALISATION STRATEGY
Provincial annual target : 40%
Achievement as at 30 September 2023 : 50.46%
68

## Slide 69: Recommendation
It is recommended that the :
Portfolio Committee note the 2nd Quarter report as presented.